# UNIVERSITY LMS

DAY 9 — DELIVERY WORK BREAKDOWN, 120-WORKING-DAY PLAN, EFFORT ESTIMATION & CRITICAL PATH

Controlled Draft v0.1  |  Day 9 of discovery  |  Planning only — NOT APPROVED

| Control | Description |
| --- | --- |
| Requirement authority | Original Day 2 atomic RTM: 152 requirement IDs; University technical requirement §§2–10 |
| Working inputs | Day 3: 55 candidate objects, 22 open clarifications; Day 4 logical ERD; Day 5 physical design; Day 6: 38 candidate APIs and 10 candidate events; Day 7 security; Day 8: 12 dependencies and 24 proposed test cases |
| Schedule basis | 120 working days approved as revised duration; phase allocation and staffing below are proposed, not approved |
| Status | DRAFT — NOT APPROVED. No vendor contract, estimate, staff allocation, requirement closure, or implementation authorization is implied. |
| Scope discipline | No extra roles, payment journeys, RAG features, or unapproved scope; original IDs and open decisions retained. |

# 1. Objectives and Day 9 outputs

Create an auditable work breakdown structure (WBS) linking all eight Day 2 requirement families to build and verification work packages.

Define a feasible 120-working-day baseline with overlaps, entry/exit gates, staffing assumptions, external dependencies and contingency.

Build a dependency-driven critical-path register; quantify only illustrative effort ranges until team velocity and vendor contracts are verified.

Identify risk owners, evidence deliverables and escalation triggers. No date is called committed without University approval.

# 2. Unchanged Day 2 atomic requirement-family baseline

| Family | Requirement IDs | Count | Day 6 design coverage |
| --- | --- | --- | --- |
| NFR | NFR-001–010 | 10 | Scale, reliability, latency evidence, DR |
| IAM | IAM-001–020 | 20 | Login, MFA, scoped RBAC, SSO, identities |
| ACD | ACD-001–023 | 23 | Academic taxonomy, course, publishing, classes, media/search |
| ASM | ASM-001–023 | 23 | Attendance, AI+SME, assessment, marksheets, records, certificates |
| COM | COM-001–022 | 22 | Dashboards, MPR, forums, calendar, notification channels |
| MOB | MOB-001–028 | 28 | Web/mobile parity, DRM, offline and device security |
| SEC | SEC-001–016 | 16 | OWASP, audit, India residency, VAPT, authz |
| OPS | OPS-001–010 | 10 | Monitoring, deployment, backups, DR, operations |

# 3. Planning principles and constraints

All 120 days are WORKING days, not calendar days. Start date, holidays, team availability, contract lead times and acceptance windows remain to be agreed.

Activities may overlap only after predecessor evidence is sufficient; design/build/test are parallel workstreams with controlled interface baselines.

The original source proposed a shorter delivery schedule; the revised 120-working-day duration governs planning, not a waiver of functional, security, mobile or scale requirements.

The 500,000-concurrent-user requirement is a performance acceptance target, not a sizing result; test workload definitions and provider limits must be approved early.

Go-live requires Android and iOS parity, independent CERT-In empanelled VAPT, DR evidence, academic record controls and external integrations.

# 4. 120-working-day master roadmap — proposed stage gates

| Phase | Working days | Workstream focus | Required outputs | Exit gate |
| --- | --- | --- | --- | --- |
| P1 | Days 1–10 | Discovery, traceability, architecture and dependency baseline | Day 1–9 draft artifacts, Day 10 approval package | G1: Scope and architecture baseline |
| P2 | Days 11–25 | Detailed contracts, UX, security, data and test architecture | Approved ERD/API contracts, test harness, procurement readiness | G2: Design readiness |
| P3 | Days 26–40 | Thin vertical slice, environments, integration proof | IAM/tenant slice, migrations, CI/CD, representative provider stubs | G3: Prove feasibility |
| P4 | Days 41–80 | Parallel feature delivery and integration | Course, assessment, credential, communications, mobile increments | G4: Functional completeness |
| P5 | Days 81–110 | System, scale, security, UAT and release hardening | Load/DR/VAPT evidence, defect closure, UAT, mobile parity | G5: Release acceptance |
| P6 | Days 111–120 | Production readiness, rollout and operational handover | Go-live checklist, training, runbooks, sign-off and hypercare entry | G6: Go-live authorization |

Note: stage windows are provisional. G2–G6 do not represent approvals; unmet dependencies can invalidate the 120-day target and require re-baselining.

# 5. Detailed work breakdown structure and traceability

| WBS | Work package | Proposed day window | Deliverable / completion evidence | RTM families | Accountable discipline |
| --- | --- | --- | --- | --- | --- |
| WP-001 | Requirements & change control | 1–10; then ongoing | Day 2 RTM, clarification closure, scope baseline, change log | All 152; all families | University PO / BA |
| WP-002 | Organization hierarchy & IAM | 11–55 | Six-role policy, SSO, OTP/MFA, tenant scope, negative tests | IAM, SEC | IAM + backend |
| WP-003 | Logical/physical data design | 11–35 | 55-object mapping, ERD, DDL migrations, indexing and audit design | IAM, ACD, ASM, SEC, OPS | Data architect / DBA |
| WP-004 | API, events & service architecture | 11–40 | 38 candidate API contracts, 10 events, idempotency and tracing | IAM, ACD, ASM, COM, OPS | Solution architect |
| WP-005 | Infrastructure, CI/CD, observability | 15–45 | India-region environment, secret controls, deployment and telemetry | NFR, SEC, OPS | DevOps / SRE |
| WP-006 | Programme/course taxonomy & authoring | 36–73 | Programme/period/subject/topic, content lifecycle, e-library | ACD | Academic backend + web |
| WP-007 | Live classroom & recordings | 35–77 | Scheduling, provider integration, access, recording/transcript | ACD, ASM, MOB | Integration + media |
| WP-008 | Assessment & SME-reviewed AI questions | 39–80 | Question review, assessments, submissions, grading and logs | ASM | Assessment team |
| WP-009 | Attendance & alerts | 43–77 | Attendance capture, absence alerts, audit | ASM, COM | Academic team |
| WP-010 | Academic record, marksheets & certificates | 45–84 | Lifetime records, Registrar signature, QR, DigiLocker | ASM, SEC | Credential team |
| WP-011 | Forums, dashboards & reports | 46–83 | Communication, reporting, MPR, custom reports | COM | Web + analytics |
| WP-012 | Notification microservice | 34–74 | In-app/email/SMS/WhatsApp/push, templates and delivery evidence | COM, MOB | Integration team |
| WP-013 | Android/iOS mobile parity | 31–90 | Hybrid app, device auth, offline/DRM, push, app-store readiness | MOB, IAM, SEC | Mobile team |
| WP-014 | Contract/integration testing | 26–100 | Mocks, provider sandboxes, negative auth, reconciliation | All families | QA + integration |
| WP-015 | Performance and 500k concurrency | 25–108 | Workload model, staged load tests, tuning, scale evidence | NFR, OPS | Performance / SRE |
| WP-016 | Security, privacy, VAPT & remediation | 20–108 | OWASP/MASVS, India residency, CERT-In VAPT, remediation | SEC, MOB, IAM | Security / QA |
| WP-017 | Backup, geo DR & operations | 35–108 | RTO/RPO drills, audit retention, runbooks and monitoring | NFR, OPS | SRE / DBA |
| WP-018 | UAT, release and operational handover | 88–120 | UAT, accessibility, store submissions, training, rollout | All families | University PO + delivery |

Windows above overlap intentionally; they are planning assumptions, not an approved integrated resource-loaded schedule. They are NOT individual person-day estimates.

# 6. Effort model, staffing and estimation confidence

| Discipline | Illustrative peak FTE | Primary contribution | Uncertainty |
| --- | --- | --- | --- |
| Product / BA / PMO | 3 | Traceability, decisions, acceptance, schedule | University decision latency |
| Architecture / data / security | 3 | Architecture, data, governance, reviews | Cross-service and tenancy decisions |
| Backend / integrations | 7 | Services, APIs, event workflows, external contracts | Provider availability |
| Web / UX | 4 | Six-role portals, content and reporting | UI scope and accessibility |
| Mobile | 3 | Hybrid Android/iOS, offline, DRM, store releases | Parity and DRM vendor |
| QA / automation / performance | 4 | E2E, contract, load and regression | 500k workload and environment |
| DevOps / SRE | 2 | CI/CD, observability, DR and operations | India regions and service limits |

Illustrative PEAK: 26 FTE, not necessarily 26 FTE for 120 days. A constant 26-person staffing level would equal 3,120 gross person-days (26 × 120), which is an upper-bound arithmetic scenario, not an approved effort estimate. Actual allocation requires work-package estimates, skill mix, ramp-up/ramp-down, leave, parallelism, vendor lead time and productivity assumptions.

| Estimate type | Proposed method | Output / gate |
| --- | --- | --- |
| Bottom-up | 3-point estimates (optimistic, most likely, pessimistic) by atomic deliverable | Expected effort and confidence interval |
| Dependency-adjusted | Predecessor/critical path and resource contention modelling | Feasible schedule and float |
| Integration allowance | Explicit sandbox, compliance and procurement lead-time risk | Named external blockers |
| Quality reserve | Include defect fixing, retest, load tuning, security remediation | No invisible zero-day buffers |
| Baseline control | Review by engineering leads, finance and University sponsor | Signed staffing/effort/schedule baseline |

# 7. Critical path candidates and external blocking conditions

| ID | Potential critical dependency | Predecessor chain | Impact if delayed | Escalation owner |
| --- | --- | --- | --- | --- |
| CP-01 | University hierarchy and six-role permissions | WP-002 → WP-003 → WP-006/008/010 | Cross-tenant security cannot be validated | University PO / IAM |
| CP-02 | SSO and identity-provider sandbox | WP-002 → WP-014 → WP-018 | Login and federation UAT blocked | University IdP owner |
| CP-03 | Live provider and DRM entitlement | WP-007 + WP-013 → WP-014 → WP-015 | Class/media capacity or offline parity blocked | Integration + mobile |
| CP-04 | Registrar signing + DigiLocker onboarding | WP-010 → WP-014 → WP-018 | Certificate acceptance blocked | Registrar / provider |
| CP-05 | Performance workload + 500k environment | WP-015 → WP-018 | No objective scale acceptance | University PO / performance |
| CP-06 | CERT-In VAPT + remediation window | WP-016 → WP-018 | Security go-live gate blocked | Security owner |
| CP-07 | DR topology and restoration evidence | WP-017 → WP-018 | RTO/RPO unverified | SRE / University IT |
| CP-08 | Mobile app accounts and store review | WP-013 → WP-018 | Concurrent go-live blocked | University mobile owner |

Critical path is provisional: true longest-path calculations require duration, precedence, calendar and resource data. Do not describe these chains as a computed CPM result.

# 8. Day 8 dependency closure plan — all 12 dependencies

# 8A. Exact Day 8 dependency inventory carried forward

| ID | Dependency | Scope function | Evidence / contract required | RTM family | Current status |
| --- | --- | --- | --- | --- | --- |
| INT-01 | Digi-Pharmed / PRTS | OAuth2 SSO | University IdP sponsor, discovery metadata, client registration, scopes, sandbox users, signed claims | IAM / SEC | Blocked until contract and credentials verified |
| INT-02 | DigiLocker | Academic credentials | University DigiLocker onboarding, issuer registration, signed-document contract, callback and consent policy | ASM / SEC | Blocked until registration and signed artifact format |
| INT-03 | Live classroom provider | HD sessions, breakout/polls/whiteboard, recordings | Provider shortlist, seat/concurrency entitlement, API/webhook, India residency, retention | ACD / MOB / NFR | Blocked until provider capabilities and load evidence |
| INT-04 | CDN / DRM / media storage | AV delivery, protected offline cache | Object store, CDN edge, DRM license/key policy, transcoding and access tests | ACD / MOB / SEC | Blocked until architecture/security approval |
| INT-05 | Email service | Notifications | Sender/domain verification, quotas, callback and template policy | COM / OPS | Provider not selected |
| INT-06 | SMS gateway | OTP and alerts | Sender registration, rate limits, delivery receipts, country/India compliance | IAM / COM | Provider not selected |
| INT-07 | WhatsApp Business | Notifications | Business account, approved templates, opt-in/consent, callback signing | COM / SEC | Provider not selected |
| INT-08 | Mobile push | Android/iOS push | App identities, APNs/FCM configuration, device token lifecycle | MOB / COM | Developer accounts and provider access pending |
| INT-09 | AI question-generation provider | Draft questions, mandatory SME review | Model API contract, prompt/data policy, review state enforcement | ASM / SEC | Provider/data handling approval pending |
| INT-10 | Registrar signature service | Digitally signed certificates and marksheets | Signer authorization, key custody, signature verification, revocation/correction policy | ASM / SEC | Signing authority pending |
| INT-11 | Mobile distribution | Concurrent Android/iOS go-live | Store accounts, signing, privacy disclosure, build/release credentials | MOB / OPS | Account and release prerequisites pending |
| INT-12 | Independent VAPT provider | CERT-In empanelled assessment | Scope, assessor engagement, report and remediation verification | SEC / OPS | Booking and test scope pending |

| Priority | Dependency IDs | Required Day 9 action | Evidence / owner |
| --- | --- | --- | --- |
| P0 | INT-01, INT-02, INT-03, INT-10 | Obtain University sponsor, technical contract, sandbox, signed authority | University SSO, Registrar, provider owners |
| P0 | INT-04, INT-12 | Confirm DRM/CDN capabilities, VAPT engagement and India-region controls | Security + integration |
| P1 | INT-05, INT-06, INT-07, INT-08 | Select messaging/push providers and onboard senders/apps | Communications + mobile |
| P1 | INT-09, INT-11 | Approve AI provider data handling, app-store accounts | Academic + mobile |

# 9. Risk register with early warning signals

| Risk | Risk description | Likelihood* | Impact* | Mitigation / trigger | Owner |
| --- | --- | --- | --- | --- | --- |
| R-01 | 500k concurrency interpretation or provider quota unresolved | High | High | Approve workload, test environment and load profiles by design gate | University PO / performance |
| R-02 | Multi-tenant hierarchy/cardinality unapproved | High | High | Close Day 3 organization decisions before final DB/IAM | University PO |
| R-03 | DigiLocker/Registrar integration lead time | High | High | Early onboarding, mock contract then sandbox proof | Registrar |
| R-04 | Live video/DRM provider capacity and residency | High | High | Provider proof of concept and load evidence | Integration lead |
| R-05 | VAPT defects late in programme | High | High | Threat modelling early, pre-assessment and remediation reserve | Security lead |
| R-06 | Mobile/web parity or store rejection | Medium | High | Parity matrix, device farm and early submission rehearsal | Mobile lead |
| R-07 | Data residency gaps in third parties/logs | Medium | High | Provider data-flow assessment and regional controls | Privacy owner |
| R-08 | Cross-service schema/API churn | High | Medium | Versioned contracts, change board, consumer tests | Architect |
| R-09 | Academic record/certificate correction policy unknown | High | High | Registrar policy workshop and immutable audit model | University registrar |
| R-10 | University approvals delay critical path | High | High | Decision SLA, escalation and recorded NO-GO | Delivery manager |
| R-11 | DR exercise fails 4h/24h targets | Medium | High | Early restoration rehearsal and runbook corrections | SRE |
| R-12 | Scope creep from unspecified payments/features | Medium | High | RTM gate and signed change request before new work | Product owner |

*Qualitative risk ratings are proposed assessments, not quantified evidence; validate likelihood, impact, reserve and ownership with the University.

# 10. Deliverable acceptance, RACI and evidence controls

| Deliverable | Responsible | Accountable approval | Required objective evidence |
| --- | --- | --- | --- |
| Scope / RTM baseline | BA + Architect | University PO | Atomic ID trace, source references, signed clarifications |
| IAM and tenant design | IAM + Data Architect | University security owner | Role matrix, cross-tenant negative tests |
| API/data contract | Backend + Data | Solution Architect | Schema, OpenAPI, compatibility and review record |
| External integration readiness | Integration team | University integration owner | Sandbox contract, quota and outage tests |
| Performance acceptance | Performance + SRE | University technical owner | 500k workload definition and observed results |
| VAPT / privacy | Security team | University security owner | CERT-In report and closure |
| Mobile/web parity | Mobile + QA | University PO | Role-by-role feature matrix and release evidence |
| DR / operational handover | SRE + DBA | University IT owner | Timed RTO/RPO drill and runbooks |
| Go-live | Delivery + all leads | Authorized University sponsor | Signed release decision and rollback plan |

# 11. Schedule control and change management

Every WBS item must include: owner, RTM IDs, entry prerequisites, test/evidence, estimated person-days, start/end, dependencies, status and sign-off.

Maintain baseline vs forecast dates, earned progress based on accepted evidence (not merely task start), blockers, defects and critical path movement.

No changes to the 152 atomic requirement statements, source classifications or earlier controlled documents without a change request, impact analysis and University approval.

Open decisions and clarifications are not implicitly accepted because a work package is scheduled; unresolved P0 items trigger escalation or a NO-GO gate.

A 120-day plan is conditional until vendor commitments, staffing, holidays, workload definition, architecture decisions and acceptance criteria are confirmed.

# 12. Day 9 verification and review scenarios

| Check ID | Acceptance / verification criterion | Status |
| --- | --- | --- |
| D9-V01 | All 152 IDs have a mapped delivery/test workstream | PLANNED — not verified |
| D9-V02 | All six roles covered in IAM and UAT | PLANNED — not verified |
| D9-V03 | All 55 logical objects remain traceable | PLANNED — not verified |
| D9-V04 | All 38 APIs and 10 events remain covered | PLANNED — not verified |
| D9-V05 | All 12 external dependencies have owner, gate and escalation | PLANNED — not verified |
| D9-V06 | All 22 Day 3 clarifications remain open until resolved | PLANNED — not verified |
| D9-V07 | All 12 Day 5, 14 Day 6, 12 Day 7, 14 Day 8 decisions retained | PLANNED — not verified |
| D9-V08 | No work package silently introduces payment workflows or extra roles | PLANNED — not verified |
| D9-V09 | 500k performance, uptime and DR have measurable acceptance evidence plans | PLANNED — not verified |
| D9-V10 | CERT-In VAPT and mobile parity included before go-live | PLANNED — not verified |
| D9-V11 | Schedule uses 120 working days, not calendar days | PLANNED — not verified |
| D9-V12 | Effort, peak FTE, reserves and dependencies are explicitly assumptions | PLANNED — not verified |
| D9-V13 | Go-live approval and rollback evidence are explicit | PLANNED — not verified |
| D9-V14 | Risk register contains trigger, owner and mitigation | PLANNED — not verified |

# 13. All upstream inventories preserved — API, events, roles and data

# 13A. All 38 Day 6 candidate APIs

| ID | Method | Candidate path | Purpose | Owner | RTM | Critical control |
| --- | --- | --- | --- | --- | --- | --- |
| IAM-API-01 | POST | /api/v1/auth/otp/challenges | Initiate OTP challenge | IAM | IAM/SEC | OTP anti-abuse; no enumeration |
| IAM-API-02 | POST | /api/v1/auth/otp/verify | Verify OTP and issue session via approved IdP | IAM | IAM/SEC | Rate limit; replay prevention |
| IAM-API-03 | GET | /api/v1/me/permissions | Effective scoped permissions | IAM | IAM | No role escalation |
| IAM-API-04 | POST | /api/v1/role-assignments | Create scoped role assignment | IAM | IAM/SEC | Admin policy; audit |
| IAM-API-05 | GET | /api/v1/sso/callback | SSO callback (provider-dependent) | IAM | IAM | State/nonce validation |
| ORG-API-01 | GET | /api/v1/institutions | List authorized institutions | Organization | IAM/ACD | Tenant filter |
| ORG-API-02 | GET | /api/v1/programmes | Programme catalogue | Academic | ACD | Scope filter |
| ORG-API-03 | GET | /api/v1/programmes/{id}/periods | Year/semester hierarchy | Academic | ACD | Validated hierarchy |
| ORG-API-04 | GET | /api/v1/subjects/{id}/topics | Topic hierarchy | Academic | ACD | Validated hierarchy |
| CRS-API-01 | POST | /api/v1/courses | Create draft course | Content | ACD | Faculty authorization |
| CRS-API-02 | POST | /api/v1/courses/{id}/versions | Create content version | Content | ACD | Immutable published history |
| CRS-API-03 | POST | /api/v1/content/{id}/review | Submit or record review | Content | ACD | State transition audit |
| CRS-API-04 | POST | /api/v1/content/{id}/publish | Publish approved version | Content | ACD | Approval prerequisite |
| CRS-API-05 | GET | /api/v1/courses/{id}/prerequisites | Check prerequisite rules | Content | ACD | No circular dependency |
| LIVE-API-01 | POST | /api/v1/live-sessions | Schedule provider session | Live | ACD | Conflict detection |
| LIVE-API-02 | GET | /api/v1/live-sessions/{id}/join | Get authorized provider join info | Live | ACD | Scoped short-lived access |
| LIVE-API-03 | GET | /api/v1/recordings/{id} | Recording metadata and access | Media | ACD/MOB | DRM/entitlement |
| SRCH-API-01 | GET | /api/v1/library/search | Search titles/docs/transcripts | Search | ACD | Visibility filters |
| ASM-API-01 | POST | /api/v1/questions/generate | Request AI-assisted draft questions | Assessment | ASM | SME review required |
| ASM-API-02 | POST | /api/v1/questions/{id}/review | SME review decision | Assessment | ASM | Reviewer authorization |
| ASM-API-03 | POST | /api/v1/assessments/{id}/attempts | Start assessment attempt | Assessment | ASM | Eligibility/idempotency |
| ASM-API-04 | POST | /api/v1/attempts/{id}/submit | Submit answers | Assessment | ASM | Exactly one accepted finalization |
| ASM-API-05 | POST | /api/v1/attendance/sessions/{id}/records | Record attendance | Attendance | ASM | Duplicate protection |
| ASM-API-06 | POST | /api/v1/practical-logbook/entries | Add logbook entry | Assessment | ASM | Faculty validation pending |
| ASM-API-07 | GET | /api/v1/academic-records/{studentId} | Authorized lifetime academic history | Records | ASM | Student/privacy rules |
| ASM-API-08 | POST | /api/v1/marksheets/{id}/sign | Digitally sign marksheet | Credentials | ASM | Authorized signing |
| ASM-API-09 | POST | /api/v1/certificates/issue | Issue numbered signed QR certificate | Credentials | ASM | Registrar authority |
| ASM-API-10 | GET | /api/v1/certificates/verify/{code} | Verify certificate authenticity | Credentials | ASM/SEC | Minimized public disclosure |
| COM-API-01 | GET | /api/v1/dashboards/me | Role dashboard | Reporting | COM | Tenant scoped |
| COM-API-02 | POST | /api/v1/reports/queries | Run authorized report definition | Reporting | COM | No arbitrary SQL |
| COM-API-03 | POST | /api/v1/forums/{id}/posts | Create forum post | Communications | COM | Visibility/moderation pending |
| COM-API-04 | POST | /api/v1/announcements | Publish announcement | Communications | COM | Audience authorization |
| COM-API-05 | GET | /api/v1/calendar | Read calendar | Communications | COM | Role-scoped events |
| COM-API-06 | POST | /api/v1/notifications/requests | Queue templated notification | Notifications | COM | Recipient policy, idempotency |
| COM-API-07 | GET | /api/v1/notifications/{id}/status | Read delivery status | Notifications | COM | No cross-tenant leakage |
| MOB-API-01 | GET | /api/v1/mobile/sync-manifest | Fetch permitted offline sync metadata | Mobile | MOB | Device entitlements |
| MOB-API-02 | POST | /api/v1/mobile/sync-receipts | Acknowledge sync state | Mobile | MOB | Conflict rules pending |
| OPS-API-01 | GET | /health/ready | Internal readiness | Platform | OPS | Not public; no secrets |

# 13B. All 10 Day 6 candidate events

| ID | Event (proposal) | Producer | Consumer | Illustrative payload | Safety rule |
| --- | --- | --- | --- | --- | --- |
| EV-01 | ContentPublished | Content | Search, analytics | contentId, version, tenantId | Outbox; projection rebuild |
| EV-02 | LiveSessionScheduled | Live | Calendar, notification | sessionId, start, providerRef | Avoid duplicate reminders |
| EV-03 | AttendanceRecorded | Attendance | Reporting, absence alerts | sessionId, learnerId, status | Idempotent alert evaluation |
| EV-04 | QuestionReviewed | Assessment | Assessment publication | questionId, reviewerDecision | Reject unapproved publication |
| EV-05 | AssessmentSubmitted | Assessment | Grade/academic record | attemptId, submittedAt | One final submission |
| EV-06 | GradeFinalized | Assessment | Academic records, reports | gradeId, version | No duplicate grade mutation |
| EV-07 | CertificateIssued | Credentials | DigiLocker, notification | certificateId, number | No duplicate issue |
| EV-08 | NotificationRequested | Notifications | Delivery adapters | notificationId, templateId | Retry + dedup + provider callback |
| EV-09 | MediaAssetReady | Media | Content/search projection | assetId, contentVersion | DRM/permission check |
| EV-10 | AuditEvidenceAnchored | Platform | Compliance storage | auditBatchId, integrityRef | Tamper evidence verification |

# 13C. Exactly six University roles

| Role | Source-described responsibility | Proposed least-privilege boundary | Authorization scope | Open approval |
| --- | --- | --- | --- | --- |
| University Super Admin | University-wide administration | Administration only within formally approved University tenant; sensitive changes require strong auth and audit | University / all institutions? | Exact privileges and cross-institution scope OPEN |
| SPC Admin | SPC administration | Scoped to explicitly assigned SPC jurisdiction and linked institutions | SPC / jurisdiction | SPC-to-institution cardinality OPEN |
| Institution Admin | Institution administration | Scoped to assigned institution, not automatically all SPC or University data | Institution | Whether one person may administer multiple institutions OPEN |
| Faculty/Educator | Teaching and course activities | Only courses/classes and learner records explicitly assigned | Course / institution | Course sharing and co-author review rights OPEN |
| Student/Learner | Learning and personal academic activities | Own enrollments, assessments, attendance, results and approved learning resources | Self / enrollment | Guardian, transfer, lifetime account mapping OPEN |
| Registered Pharmacist | Professional learning role | Only authorized pharmacist learning/credential features after identity verification | Self / verified professional identity | Exact differentiation from Student and professional verification OPEN |

# 13D. Logical object catalogue — part A

| Object ID | Candidate object | Attributes from Day 4 | Day 2 RTM |
| --- | --- | --- | --- |
| ORG-01 | University | university_id, display_name, status | IAM-001, IAM-016 |
| ORG-02 | SPC jurisdiction | spc_id, name, parent_reference | IAM-002, IAM-016 |
| ORG-03 | Institution | institution_id, name, organization_reference | IAM-003, IAM-016 |
| IAM-OBJ-01 | User identity | user_id, identity_provider_ref, status | IAM-007..015 |
| IAM-OBJ-02 | Role definition | role_id, role_code, role_name | IAM-001..008 |
| IAM-OBJ-03 | Permission | permission_id, resource, action | IAM-008, IAM-017 |
| IAM-OBJ-04 | Role–permission grant | role_id, permission_id, scope | IAM-008, IAM-017 |
| IAM-OBJ-05 | User membership/role assignment | user_id, organization_id, role_id, validity | IAM-007..008, IAM-016 |
| IAM-OBJ-06 | Provisioning/import batch | batch_id, initiator, outcome | IAM-018..020 |
| IAM-OBJ-07 | External SSO link | user_id, provider, subject_ref | IAM-015 |

# 13E. Logical object catalogue — part B

| Object ID | Candidate object | Attributes from Day 4 | Day 2 RTM |
| --- | --- | --- | --- |
| ACD-OBJ-01 | Programme | programme_id, name, status | ACD-001 |
| ACD-OBJ-02 | Year/Semester | period_id, programme_id, label | ACD-002 |
| ACD-OBJ-03 | Subject | subject_id, period_id, title | ACD-003 |
| ACD-OBJ-04 | Topic | topic_id, subject_id, title | ACD-004 |
| ACD-OBJ-05 | Course | course_id, academic_ref, status | ACD-005 |
| ACD-OBJ-06 | Course prerequisite | course_id, required_course_ref, rule | ACD-006 |
| ACD-OBJ-07 | Content item | content_id, course_ref, content_type | ACD-005, ACD-020 |
| ACD-OBJ-08 | Content version | content_id, version, approval_state | ACD-008..009 |
| ACD-OBJ-09 | Content contributor | content_id, user_id, contribution_role | ACD-007 |
| ACD-OBJ-10 | Content approval event | version_ref, actor, transition, timestamp | ACD-008..009 |
| ACD-OBJ-11 | Live class session | session_id, course_ref, provider_ref | ACD-010..015 |
| ACD-OBJ-12 | Class schedule | session_id, planned_time, resource_ref | ACD-018..019 |
| ACD-OBJ-13 | Recording / transcript metadata | session_id, asset_ref, transcript_ref | ACD-015..017 |
| ACD-OBJ-14 | Library index record | content_ref, title, searchable_text_ref | ACD-020..023 |

# 13F. Logical object catalogue — part C

| Object ID | Candidate object | Attributes from Day 4 | Day 2 RTM |
| --- | --- | --- | --- |
| ASM-OBJ-01 | Attendance record | session_ref, person_ref, status, time | ASM-001..004 |
| ASM-OBJ-02 | Absence notification trigger | attendance_ref, recipient_scope, status | ASM-002..004 |
| ASM-OBJ-03 | Question bank item | question_id, subject_ref, version, state | ASM-005 |
| ASM-OBJ-04 | AI question draft | draft_id, prompt_ref, reviewer_status | ASM-006..007 |
| ASM-OBJ-05 | SME review decision | draft_ref, reviewer_ref, decision, timestamp | ASM-007 |
| ASM-OBJ-06 | Assessment definition | assessment_id, chapter_ref, delivery_scope | ASM-008..009 |
| ASM-OBJ-07 | Assessment attempt / response | attempt_id, learner_ref, response_ref | ASM-008..011 |
| ASM-OBJ-08 | Grade / grading event | attempt_ref, grader_ref, score, event | ASM-010..011 |
| ASM-OBJ-09 | Assignment | assignment_id, course_ref, due_rule | ASM-012..013 |
| ASM-OBJ-10 | Assignment submission | assignment_ref, learner_ref, submission_ref | ASM-012..013 |
| ASM-OBJ-11 | Practical logbook entry | learner_ref, practical_ref, evidence_ref | ASM-014 |
| ASM-OBJ-12 | Marksheets | marksheet_id, learner_ref, signature_ref | ASM-015..016 |
| ASM-OBJ-13 | Lifetime academic record | learner_ref, record_ref, achievement_ref | ASM-017 |
| ASM-OBJ-14 | Certificate | certificate_id, unique_number, learner_ref | ASM-018..023 |
| ASM-OBJ-15 | Certificate verification | certificate_ref, verification_token, state | ASM-021..022 |
| ASM-OBJ-16 | Credential integration receipt | certificate_ref, provider_ref, result | ASM-023 |

# 13G. Logical object catalogue — part D

| Object ID | Candidate object | Attributes from Day 4 | Day 2 RTM |
| --- | --- | --- | --- |
| COM-OBJ-01 | Dashboard/report definition | report_id, owner_scope, specification | COM-001..009 |
| COM-OBJ-02 | Reporting projection | source_ref, metric_key, period, value | COM-006..009, COM-022 |
| COM-OBJ-03 | Forum / discussion item | thread_id, course_ref, author_ref | COM-010 |
| COM-OBJ-04 | Announcement | announcement_id, audience_scope, message | COM-011 |
| COM-OBJ-05 | Platform message | message_id, sender_ref, recipient_scope | COM-012 |
| COM-OBJ-06 | Academic calendar event | event_id, academic_scope, start_time | COM-013 |
| COM-OBJ-07 | Notification template | template_id, channel, version | COM-014..020 |
| COM-OBJ-08 | Notification request | request_id, event_ref, channel, status | COM-014..019 |
| COM-OBJ-09 | Delivery attempt/receipt | request_id, provider_ref, delivery_state | COM-021 |
| MOB-OBJ-01 | Playback/bookmark/notes | learner_ref, media_ref, position, note_ref | MOB-015..021 |
| MOB-OBJ-02 | Device notification preference | user_ref, channel, preference | MOB-023..025 |
| MOB-OBJ-03 | Offline cache manifest | device_ref, asset_ref, expiry | MOB-026 |
| SEC-OBJ-01 | Tamper-evident audit event | event_id, actor, action, integrity_ref | IAM-020, SEC-005..007, SEC-016 |
| OPS-OBJ-01 | Test / acceptance evidence | test_id, RTM_id, result, evidence_ref | OPS-005..010 |
| OPS-OBJ-02 | External integration transaction | integration_id, provider, correlation_ref, status | IAM-015, ASM-023, COM-018 |

# 14. All upstream clarification and decision registers — unchanged

# 14A. All 22 Day 3 clarifications

| Clarification ID | Decision required (unchanged) | Proposed owner | Status |
| --- | --- | --- | --- |
| D3-CL-01 | University / SPC / Institution parent-child cardinalities and whether hierarchy can change | University sponsor | OPEN |
| D3-CL-02 | Whether one person may hold multiple roles and roles in multiple institutions | University IAM owner | OPEN |
| D3-CL-03 | Approved permission matrix per role and tenant, including pharmacist access | University IAM owner | OPEN |
| D3-CL-04 | Student enrolment ownership and transfer between institutions | Academic SME | OPEN |
| D3-CL-05 | Academic taxonomy reuse and relationship between Course and Programme/Subject/Topic | Academic SME | OPEN |
| D3-CL-06 | Prerequisite equivalence, overrides and cycle prevention | Academic SME | OPEN |
| D3-CL-07 | Content approver authority, publish/rollback, version immutability | Content SME | OPEN |
| D3-CL-08 | Live class attendance source, scheduling conflict rules, recording retention | Academic/IT SME | OPEN |
| D3-CL-09 | Question/SME reviewer authorization, AI data-sharing and audit expectations | Assessment SME | OPEN |
| D3-CL-10 | Assessment attempt, retake, grading, correction and result-release rules | Assessment SME | OPEN |
| D3-CL-11 | Lifetime record meaning, correction, archival and migration | Registrar | OPEN |
| D3-CL-12 | Certificate revocation/reissue, QR public data fields, signing authority | Registrar | OPEN |
| D3-CL-13 | Report metric definitions, MPR format, SLA calculations and data freshness | University reporting owner | OPEN |
| D3-CL-14 | Notification preference precedence, provider retries, retention and consent | University communications owner | OPEN |
| D3-CL-15 | Mobile offline scope, cache expiry, synchronization and conflict resolution | Mobile/product owner | OPEN |
| D3-CL-16 | Concurrency workload definition, API latency targets, content volumes | University technical owner | OPEN |
| D3-CL-17 | Provider contracts/sandbox credentials for SSO, live class, DigiLocker, messaging, DRM | Integration owners | OPEN |
| D3-CL-18 | Data classification, retention schedule (except explicit obligations), deletion and legal holds | University security/legal | OPEN |
| D3-CL-19 | Payment scope: title/service label exists, but no defined payment business workflow | University business owner | OPEN |
| D3-CL-20 | Formal approval of 120-working-day plan against source 12-week roadmap | University sponsor / PMO | OPEN |
| D3-CL-21 | Who approves ERD, schema changes and organization-scoped data access | University sponsor / architecture board | OPEN |
| D3-CL-22 | Role-specific data access and reporting for Registered Pharmacist | University business owner | OPEN |

# 14B. All 12 Day 5 decisions

| Decision ID | Question / decision (unchanged) | Status |
| --- | --- | --- |
| D5-DEC-01 | Select PostgreSQL deployment/version, extension policy and India regions | OPEN — approval required |
| D5-DEC-02 | Approve UUID/BIGINT primary key strategy per domain | OPEN — approval required |
| D5-DEC-03 | Approve tenant-scoping and RLS strategy after organizational cardinalities | OPEN — approval required |
| D5-DEC-04 | Approve schema/service ownership and cross-domain data exchange | OPEN — approval required |
| D5-DEC-05 | Approve academic/attendance/assessment uniqueness grains | OPEN — approval required |
| D5-DEC-06 | Approve record retention, legal holds and correction workflows | OPEN — approval required |
| D5-DEC-07 | Approve index/workload measurement and partition thresholds | OPEN — approval required |
| D5-DEC-08 | Approve schema migration tooling, release controls and DBA access | OPEN — approval required |
| D5-DEC-09 | Approve backup, PITR and geo-DR topology with measured drills | OPEN — approval required |
| D5-DEC-10 | Approve public certificate verification data disclosure policy | OPEN — approval required |
| D5-DEC-11 | Approve outbox/integration replay semantics | OPEN — approval required |
| D5-DEC-12 | Approve Day 5 physical baseline before implementation | OPEN — approval required |

# 14C. All 14 Day 6 decisions

| Decision ID | Open decision | Status |
| --- | --- | --- |
| D6-DEC-01 | Approve bounded context ownership and deployable service grouping | OPEN — no approval recorded |
| D6-DEC-02 | Approve OpenAPI versioning, compatibility and deprecation rules | OPEN — no approval recorded |
| D6-DEC-03 | Approve identity token flow, SSO callback and six-role resource authorization matrix | OPEN — no approval recorded |
| D6-DEC-04 | Approve OTP/MFA/session semantics and anti-abuse controls | OPEN — no approval recorded |
| D6-DEC-05 | Approve state transitions and approval owners for course publishing | OPEN — no approval recorded |
| D6-DEC-06 | Approve live-class provider contracts, calendar conflict and webhook rules | OPEN — no approval recorded |
| D6-DEC-07 | Approve question SME-review and assessment/attendance business idempotency | OPEN — no approval recorded |
| D6-DEC-08 | Approve certificate signing, DigiLocker handoff, correction and disclosure rules | OPEN — no approval recorded |
| D6-DEC-09 | Approve notification channel adapters, retry windows and templates | OPEN — no approval recorded |
| D6-DEC-10 | Approve event delivery semantics, outbox ownership and retention | OPEN — no approval recorded |
| D6-DEC-11 | Approve mobile offline synchronization and DRM authorization | OPEN — no approval recorded |
| D6-DEC-12 | Approve 500k-user workload, rate limits, SLOs and contract-test gates | OPEN — no approval recorded |
| D6-DEC-13 | Approve data residency and VAPT scope across external providers | OPEN — no approval recorded |
| D6-DEC-14 | Approve API security/privacy review and contract sign-off process | OPEN — no approval recorded |

# 14D. All 12 Day 7 decisions

| Decision ID | Decision / required owner | Status |
| --- | --- | --- |
| D7-DEC-01 | Approve six-role permission matrix by action and resource scope | OPEN — not approved |
| D7-DEC-02 | Resolve University/SPC/institution hierarchy and cross-tenant exception policy | OPEN — not approved |
| D7-DEC-03 | Confirm multi-role membership, delegation, session scope and role revocation | OPEN — not approved |
| D7-DEC-04 | Approve Registrar signing authority without inventing seventh role | OPEN — not approved |
| D7-DEC-05 | Approve SSO token mapping, OTP/MFA flows and session lifecycle | OPEN — not approved |
| D7-DEC-06 | Approve service-to-service trust, broker ACL and callback verification | OPEN — not approved |
| D7-DEC-07 | Approve provider inventory, contracts, sandboxes and India residency evidence | OPEN — not approved |
| D7-DEC-08 | Approve media DRM, recording entitlement and offline revocation rules | OPEN — not approved |
| D7-DEC-09 | Approve public QR verifier minimal response and anti-abuse rules | OPEN — not approved |
| D7-DEC-10 | Approve notification channel consent, templates and retry policy | OPEN — not approved |
| D7-DEC-11 | Approve security acceptance test evidence, VAPT and remediation gate | OPEN — not approved |
| D7-DEC-12 | Approve Day 7 authorization and integration contract baseline | OPEN — not approved |

# 14E. All 14 Day 8 decisions

| ID | Decision | State |
| --- | --- | --- |
| D8-DEC-01 | Approve integration owners, provider inventory and sandbox access | OPEN — approval required |
| D8-DEC-02 | Approve exact SSO/Digi-Pharmed/PRTS identity mapping and trust contracts | OPEN — approval required |
| D8-DEC-03 | Approve DigiLocker onboarding, Registrar signing and certificate disclosures | OPEN — approval required |
| D8-DEC-04 | Approve live-class/recording provider and concurrency entitlements | OPEN — approval required |
| D8-DEC-05 | Approve DRM/CDN/media residency and offline revocation behavior | OPEN — approval required |
| D8-DEC-06 | Approve messaging providers, consent, templates and rate quotas | OPEN — approval required |
| D8-DEC-07 | Approve AI question-generation data handling and SME review contract | OPEN — approval required |
| D8-DEC-08 | Approve end-to-end sequence and failure handling contracts | OPEN — approval required |
| D8-DEC-09 | Approve 500k concurrency interpretation and workload profile | OPEN — approval required |
| D8-DEC-10 | Approve p95/p99, TPS, soak duration and error thresholds (not in source) | OPEN — approval required |
| D8-DEC-11 | Approve India residency, audit retention and DR evidence methods | OPEN — approval required |
| D8-DEC-12 | Approve integration harness and synthetic data policies | OPEN — approval required |
| D8-DEC-13 | Approve CERT-In VAPT engagement, remediation and mobile security gate | OPEN — approval required |
| D8-DEC-14 | Approve Day 8 baseline and Day 9 transition | OPEN — approval required |

# 15. New Day 9 planning decisions — none pre-approved

| Decision ID | Required approval | Status |
| --- | --- | --- |
| D9-DEC-01 | Approve 120-day stage allocations, gates and acceptance owners | OPEN — not approved |
| D9-DEC-02 | Approve baseline calendar, working-day definition, holidays and start date | OPEN — not approved |
| D9-DEC-03 | Approve detailed WBS, RTM mapping and scope exclusions | OPEN — not approved |
| D9-DEC-04 | Approve team availability, role mix, ramp-up and budget | OPEN — not approved |
| D9-DEC-05 | Approve three-point effort estimates, risk reserves and contingency | OPEN — not approved |
| D9-DEC-06 | Approve provider procurement, onboarding lead times and contractual SLAs | OPEN — not approved |
| D9-DEC-07 | Approve true CPM network after precedence and durations are supplied | OPEN — not approved |
| D9-DEC-08 | Approve 500k workload model and measurable NFR acceptance thresholds | OPEN — not approved |
| D9-DEC-09 | Approve VAPT, DR, UAT and mobile-store lead-time reservations | OPEN — not approved |
| D9-DEC-10 | Approve risk appetite, escalation thresholds and decision SLAs | OPEN — not approved |
| D9-DEC-11 | Approve Day 10 scope/design readiness pack inputs | OPEN — not approved |
| D9-DEC-12 | Authorize or withhold transition beyond discovery gate | OPEN — not approved |

# 16. Day 9 exit criteria and Day 10 handoff

Day 9 deliverables: WBS, stage plan, assumptions-based staffing/effort model, critical-path candidates, dependency priorities, risks, review tests, open decision register and approval table.

Day 9 exit is a DOCUMENT COMPLETION gate only. Approval requires University sponsor, solution architect, security, QA, integration, SRE and delivery management sign-off.

Day 10 proposed focus: consolidated discovery review, evidence/clarification closure, source-to-RTM-to-WBS crosswalk, scope/design gate decision and 120-day baseline authorization.

# 17. Approval register

| Reviewer | Status | Date / evidence |
| --- | --- | --- |
| University Product Owner | PENDING | — |
| University IT / Integration Owner | PENDING | — |
| Solution Architect | PENDING | — |
| Security / Privacy Lead | PENDING | — |
| QA / Performance Lead | PENDING | — |
| SRE / Data Lead | PENDING | — |
| Delivery Manager / PMO | PENDING | — |