# UNIVERSITY LMS

DAY 10 — CONSOLIDATED DISCOVERY REVIEW, TRACEABILITY AUDIT & FORMAL READINESS GATE

Draft v0.1 | Gate G-D10: NOT APPROVED | Day 10 of 120 working days | No implementation authorization

| Document control | Value |
| --- | --- |
| Scope and identity | UNIVERSITY LMS exclusively; University technical requirements §§2–10 |
| Source baseline | Original Day 2: 152 atomic requirement IDs in eight families; Day 1 scope discovery; Days 3–9 working drafts |
| Gate | Consolidated discovery exit / authorization to proceed to detailed design, not to start development |
| Review status | Proposed audit findings; evidence not independently signed off; no approval assumed |
| Change discipline | Preserve original ID, wording, provenance and source classifications. Proposed design never upgrades to mandatory scope without change control. |

# 1. Executive readiness assessment

Decision recommendation: CONDITIONAL NO-GO for formal baseline approval until the identified source, cardinality, integration, acceptance and estimation decisions have accountable owners and documented disposition. Work on non-committal design exploration may continue only under University governance; this report does not grant implementation approval.

| Dimension | Day 10 assessment | Evidence gap / next action |
| --- | --- | --- |
| Scope baseline | Known eight families / 152 IDs; full source-to-ID verification remains required | Reconcile original RTM against University source, not just category totals |
| Architecture | Candidate logical and physical designs; 55 logical objects | Approve entity cardinality, data ownership, tenant hierarchy and record lifecycle |
| Contracts | 38 candidate APIs; 10 candidate events | Contract owners, security and consumer/provider sign-off |
| Identity/security | Exactly six application roles; proposed deny-by-default policies | Role matrix, SSO, Registrar authority, India residency, audit and VAPT plan |
| Integrations | 12 tracked dependencies, many unconfirmed | Contracts, sandbox access, quotas and responsible parties |
| Nonfunctional | 500k concurrent users, 99.5% uptime, RTO≤4h, RPO≤24h | Define workload, measurable tests, and accountable acceptance owners |
| Delivery | 120 working days; 18 work packages and illustrative 26 FTE peak | Bottom-up estimation, resource commitments, predecessor logic and cost |
| Approvals | Prior drafts explicitly NOT APPROVED | Collect documented signatures and evidence links |

# 2. Original Day 2 atomic RTM coverage control

# 2A. Complete family-level ID inventory — unchanged

| Family | Requirement IDs | Count | Day 6 design coverage |
| --- | --- | --- | --- |
| NFR | NFR-001–010 | 10 | Scale, reliability, latency evidence, DR |
| IAM | IAM-001–020 | 20 | Login, MFA, scoped RBAC, SSO, identities |
| ACD | ACD-001–023 | 23 | Academic taxonomy, course, publishing, classes, media/search |
| ASM | ASM-001–023 | 23 | Attendance, AI+SME, assessment, marksheets, records, certificates |
| COM | COM-001–022 | 22 | Dashboards, MPR, forums, calendar, notification channels |
| MOB | MOB-001–028 | 28 | Web/mobile parity, DRM, offline and device security |
| SEC | SEC-001–016 | 16 | OWASP, audit, India residency, VAPT, authz |
| OPS | OPS-001–010 | 10 | Monitoring, deployment, backups, DR, operations |

152 is the number of IDs in the known Day 2 baseline (10+20+23+23+22+28+16+10); it is not a claim that every atomic wording was reverified against the source in this document.

For each atomic requirement, require: immutable ID, exact source clause, exact original text, mandatory/recommended/clarification class, actor/tenant scope, design object, API/event if applicable, test case, owner, status and evidence link.

No row may be marked implemented, tested or approved solely because a proposed API, logical object or test name exists. Open source ambiguities remain open.

No invented payment functionality, seventh application role, RAG-based question generation, or unapproved user stories are permitted.

# 3. Discovery audit control matrix

| Control ID | Audit check | Expected evidence | Status |
| --- | --- | --- | --- |
| G10-A01 | Source document coverage §§2–10 | Clause-level source crosswalk | REVIEW REQUIRED |
| G10-A02 | All 152 IDs unique and stable | Automated uniqueness and family count report | COUNT KNOWN; WORDING RECHECK |
| G10-A03 | All mandatory requirements linked to verification | Atomic RTM with test links | OPEN |
| G10-A04 | Recommended stack not mislabelled mandatory | Technology decision record | OPEN |
| G10-A05 | No undocumented scope creep | Scope delta and exclusion register | OPEN |
| G10-A06 | Six roles and no extra invented application roles | Approved role-permission matrix | OPEN |
| G10-A07 | 55 candidate objects reconciled with workflows | Logical/physical mapping and ownership | OPEN |
| G10-A08 | 38 APIs and 10 events reviewed | OpenAPI/event schema review | OPEN |
| G10-A09 | 12 external dependencies tracked | Contract, owner, sandbox evidence | OPEN |
| G10-A10 | Performance and DR criteria testable | Signed workload and DR test plan | OPEN |
| G10-A11 | India residency and five-year audit controls | Data-flow, vendor and retention evidence | OPEN |
| G10-A12 | Mobile parity, DRM and offline security | Device matrix and parity evidence plan | OPEN |
| G10-A13 | Human SME approval for AI questions | Workflow and negative test | OPEN |
| G10-A14 | Registrar signing/DigiLocker | Authority, consent and integration contract | OPEN |
| G10-A15 | 120-day work packages and critical path | Approved WBS, estimates and resource plan | OPEN |
| G10-A16 | Approval records and baselines immutable | Signed gate minutes and version hashes | OPEN |

# 4. Requirements by workstream: coverage vs gaps

| Workstream | Required scope from source | Current design artefacts | Approval blocker |
| --- | --- | --- | --- |
| Tenant/IAM | University/SPC/Institution + six roles, OTP, 2FA, admin MFA, SSO | Role matrix, tenant model, proposed policies | Org cardinality, multiple roles, identity mapping |
| Academic catalogue | Programme → Year/Semester → Subject → Topic, gating, versioning | 55-object catalogue, API proposal | Hierarchy reuse and author/publish rights |
| Live learning | HD classes, whiteboard, breakout, polls, recording, transcripts | Live-session sequences, provider dependency | Vendor quota, recording access and consent |
| Assessments | Attendance, assignments, grading, human-reviewed AI questions | Assessment sequences and test candidates | Grading, retakes, SME authority and data lifecycle |
| Records/certificates | Lifetime academic record, signed marksheets, QR, DigiLocker | Certificate registry and integration sequence | Registrar authority, correction and public fields |
| Communication | Reports, forums, announcements, calendar, messaging, notifications | Events and notification contracts | Consent, channel providers and templates |
| Mobile | Android8+/iOS14+, parity, offline, DRM, biometrics | Mobile data, sequence and security proposals | Offline revocation, app release dependencies |
| Security/operations | India residency, OWASP, VAPT, audit≥5y, DR | Threat model, migration/DR proposals | Evidence and independent testing |
| Performance | 500,000 concurrent, CDN AV, ≥99.5% O&M | Load and NFR acceptance plans | Workload definition, capacity and vendor proof |

# 5. Discovery issues and material blockers

| Blocker | Consequence if unresolved | Closure evidence | Owner (proposed) |
| --- | --- | --- | --- |
| BLK-01 Organization/SPC/institution cardinality | Wrong tenancy and permissions | Signed hierarchy and assignment examples | University PO / IAM |
| BLK-02 Role scope and Registrar authority | Unauthorized grades/certificates | Approved role matrix and signer trust model | University security / Registrar |
| BLK-03 Source-level atomic RTM audit | Missing or invented acceptance criteria | Reviewed clause-to-ID-to-test mapping | Business analyst / QA |
| BLK-04 Integration vendors and credentials | Untestable API and release blockers | Provider contract, sandbox, quota and security acceptance | Integration lead |
| BLK-05 Concurrency workload definition | Invalid capacity design and budget | Peak scenarios, TPS, session model and sign-off | Performance lead |
| BLK-06 Data retention/correction/residency | Compliance and recovery risk | Policy, region map, data flow and deletion rules | Security/privacy |
| BLK-07 Estimation and staffing | Unreliable 120-day commitment | Bottom-up WBS, 26 FTE assumption validation | Delivery manager |
| BLK-08 Mobile/live-provider dependencies | Go-live and parity risk | App-store accounts, DRM, live vendor capacity | Mobile lead |
| BLK-09 Formal review sign-offs | Uncontrolled scope/architecture baseline | Signed gate record and decision log | University sponsor |

# 6. Proposed acceptance gate: G-D10

| Gate criterion | Pass evidence | Disposition |
| --- | --- | --- |
| G-D10-01 Source scope integrity | Original source + RTM + gap report reviewed | OPEN |
| G-D10-02 Clarification ownership | All open questions assigned and critical blockers resolved or explicitly risk-accepted | OPEN |
| G-D10-03 Architecture traceability | ERD, data dictionary, API/event inventories and decisions linked to IDs | OPEN |
| G-D10-04 IAM and security | Role matrix, threat review, residency/audit policy and VAPT plan accepted | OPEN |
| G-D10-05 Integration feasibility | Provider contracts, sandbox readiness and alternatives documented | OPEN |
| G-D10-06 NFR testability | 500k workload, availability, DR and mobile acceptance metrics signed | OPEN |
| G-D10-07 Delivery feasibility | Bottom-up estimation, resources, milestones and risks approved | OPEN |
| G-D10-08 Change control | Approved versioned baseline and exception process | OPEN |
| G-D10-09 Decision authority | Signed review minutes and approval record | OPEN |

# 7. Gate decision rules

GO: all mandatory criteria pass with linked evidence and named approvers; authorize only the explicitly approved next phase.

CONDITIONAL GO: limited design-only work can proceed with time-bound, documented exceptions, owners and explicit University risk acceptance; no affected implementation or production commitments.

NO-GO: missing critical security, source traceability, tenancy, integration feasibility, or delivery commitment evidence. This is the current recommended decision until closure.

Any exception must state the requirement IDs affected, risk, owner, expiry, compensating control and approving authority.

# 8. Day 10 verification scenarios

| Test ID | Proposed check | Trace |
| --- | --- | --- |
| D10-T01 | Cross-check all 152 ID strings and family counts | RTM / source |
| D10-T02 | Find source clause with no RTM entry | Requirements |
| D10-T03 | Find RTM item without source clause | Scope |
| D10-T04 | Detect role added beyond six | IAM |
| D10-T05 | Detect unapproved payment workflow | Scope |
| D10-T06 | Trace academic record to data, API and test | ASM |
| D10-T07 | Trace 500k concurrency to signed workload test | NFR |
| D10-T08 | Trace geo-DR RTO/RPO to exercise | NFR / OPS |
| D10-T09 | Trace India residency to all vendor regions | SEC |
| D10-T10 | Trace human SME review to negative publish test | ASM |
| D10-T11 | Trace mobile offline entitlement to revocation test | MOB |
| D10-T12 | Trace audit ≥5y to integrity/retention evidence | SEC |
| D10-T13 | Trace each provider to contract and sandbox | Integrations |
| D10-T14 | Validate WBS predecessor and owner completeness | Plan |
| D10-T15 | Verify no open issue silently marked approved | Governance |
| D10-T16 | Verify no development approval inferred | Governance |

# 9. Day 9 six-phase delivery plan — unchanged

# 9A. Phase and exit gate baseline

| Phase | Working days | Workstream focus | Required outputs | Exit gate |
| --- | --- | --- | --- | --- |
| P1 | Days 1–10 | Discovery, traceability, architecture and dependency baseline | Day 1–9 draft artifacts, Day 10 approval package | G1: Scope and architecture baseline |
| P2 | Days 11–25 | Detailed contracts, UX, security, data and test architecture | Approved ERD/API contracts, test harness, procurement readiness | G2: Design readiness |
| P3 | Days 26–40 | Thin vertical slice, environments, integration proof | IAM/tenant slice, migrations, CI/CD, representative provider stubs | G3: Prove feasibility |
| P4 | Days 41–80 | Parallel feature delivery and integration | Course, assessment, credential, communications, mobile increments | G4: Functional completeness |
| P5 | Days 81–110 | System, scale, security, UAT and release hardening | Load/DR/VAPT evidence, defect closure, UAT, mobile parity | G5: Release acceptance |
| P6 | Days 111–120 | Production readiness, rollout and operational handover | Go-live checklist, training, runbooks, sign-off and hypercare entry | G6: Go-live authorization |

# 9B. All 18 work packages — unchanged

| WBS | Work package | Proposed day window | Deliverable / completion evidence | RTM families | Accountable discipline |
| --- | --- | --- | --- | --- | --- |
| WP-001 | Requirements & change control | 1–10; then ongoing | Day 2 RTM, clarification closure, scope baseline, change log | All 152; all families | University PO / BA |
| WP-002 | Organization hierarchy & IAM | 11–55 | Six-role policy, SSO, OTP/MFA, tenant scope, negative tests | IAM, SEC | IAM + backend |
| WP-003 | Logical/physical data design | 11–35 | 55-object mapping, ERD, DDL migrations, indexing and audit design | IAM, ACD, ASM, SEC, OPS | Data architect / DBA |
| WP-004 | API, events & service architecture | 11–40 | 38 candidate API contracts, 10 events, idempotency and tracing | IAM, ACD, ASM, COM, OPS | Solution architect |
| WP-005 | Infrastructure, CI/CD, observability | 15–45 | India-region environment, secret controls, deployment and telemetry | NFR, SEC, OPS | DevOps / SRE |
| WP-006 | Programme/course taxonomy & authoring | 36–73 | Programme/period/subject/topic, content lifecycle, e-library | ACD | Academic backend + web |
| WP-007 | Live classroom & recordings | 35–77 | Scheduling, provider integration, access, recording/transcript | ACD, ASM, MOB | Integration + media |
| WP-008 | Assessment & SME-reviewed AI questions | 39–80 | Question review, assessments, submissions, grading and logs | ASM | Assessment team |
| WP-009 | Attendance & alerts | 43–77 | Attendance capture, absence alerts, audit | ASM, COM | Academic team |
| WP-010 | Academic record, marksheets & certificates | 45–84 | Lifetime records, Registrar signature, QR, DigiLocker | ASM, SEC | Credential team |
| WP-011 | Forums, dashboards & reports | 46–83 | Communication, reporting, MPR, custom reports | COM | Web + analytics |
| WP-012 | Notification microservice | 34–74 | In-app/email/SMS/WhatsApp/push, templates and delivery evidence | COM, MOB | Integration team |
| WP-013 | Android/iOS mobile parity | 31–90 | Hybrid app, device auth, offline/DRM, push, app-store readiness | MOB, IAM, SEC | Mobile team |
| WP-014 | Contract/integration testing | 26–100 | Mocks, provider sandboxes, negative auth, reconciliation | All families | QA + integration |
| WP-015 | Performance and 500k concurrency | 25–108 | Workload model, staged load tests, tuning, scale evidence | NFR, OPS | Performance / SRE |
| WP-016 | Security, privacy, VAPT & remediation | 20–108 | OWASP/MASVS, India residency, CERT-In VAPT, remediation | SEC, MOB, IAM | Security / QA |
| WP-017 | Backup, geo DR & operations | 35–108 | RTO/RPO drills, audit retention, runbooks and monitoring | NFR, OPS | SRE / DBA |
| WP-018 | UAT, release and operational handover | 88–120 | UAT, accessibility, store submissions, training, rollout | All families | University PO + delivery |

# 9C. Staffing assumptions — unchanged

| Discipline | Illustrative peak FTE | Primary contribution | Uncertainty |
| --- | --- | --- | --- |
| Product / BA / PMO | 3 | Traceability, decisions, acceptance, schedule | University decision latency |
| Architecture / data / security | 3 | Architecture, data, governance, reviews | Cross-service and tenancy decisions |
| Backend / integrations | 7 | Services, APIs, event workflows, external contracts | Provider availability |
| Web / UX | 4 | Six-role portals, content and reporting | UI scope and accessibility |
| Mobile | 3 | Hybrid Android/iOS, offline, DRM, store releases | Parity and DRM vendor |
| QA / automation / performance | 4 | E2E, contract, load and regression | 500k workload and environment |
| DevOps / SRE | 2 | CI/CD, observability, DR and operations | India regions and service limits |

# 9D. Critical path candidates — unchanged

| ID | Potential critical dependency | Predecessor chain | Impact if delayed | Escalation owner |
| --- | --- | --- | --- | --- |
| CP-01 | University hierarchy and six-role permissions | WP-002 → WP-003 → WP-006/008/010 | Cross-tenant security cannot be validated | University PO / IAM |
| CP-02 | SSO and identity-provider sandbox | WP-002 → WP-014 → WP-018 | Login and federation UAT blocked | University IdP owner |
| CP-03 | Live provider and DRM entitlement | WP-007 + WP-013 → WP-014 → WP-015 | Class/media capacity or offline parity blocked | Integration + mobile |
| CP-04 | Registrar signing + DigiLocker onboarding | WP-010 → WP-014 → WP-018 | Certificate acceptance blocked | Registrar / provider |
| CP-05 | Performance workload + 500k environment | WP-015 → WP-018 | No objective scale acceptance | University PO / performance |
| CP-06 | CERT-In VAPT + remediation window | WP-016 → WP-018 | Security go-live gate blocked | Security owner |
| CP-07 | DR topology and restoration evidence | WP-017 → WP-018 | RTO/RPO unverified | SRE / University IT |
| CP-08 | Mobile app accounts and store review | WP-013 → WP-018 | Concurrent go-live blocked | University mobile owner |

# 9E. All 12 Day 9 risks — unchanged

| Risk | Risk description | Likelihood* | Impact* | Mitigation / trigger | Owner |
| --- | --- | --- | --- | --- | --- |
| R-01 | 500k concurrency interpretation or provider quota unresolved | High | High | Approve workload, test environment and load profiles by design gate | University PO / performance |
| R-02 | Multi-tenant hierarchy/cardinality unapproved | High | High | Close Day 3 organization decisions before final DB/IAM | University PO |
| R-03 | DigiLocker/Registrar integration lead time | High | High | Early onboarding, mock contract then sandbox proof | Registrar |
| R-04 | Live video/DRM provider capacity and residency | High | High | Provider proof of concept and load evidence | Integration lead |
| R-05 | VAPT defects late in programme | High | High | Threat modelling early, pre-assessment and remediation reserve | Security lead |
| R-06 | Mobile/web parity or store rejection | Medium | High | Parity matrix, device farm and early submission rehearsal | Mobile lead |
| R-07 | Data residency gaps in third parties/logs | Medium | High | Provider data-flow assessment and regional controls | Privacy owner |
| R-08 | Cross-service schema/API churn | High | Medium | Versioned contracts, change board, consumer tests | Architect |
| R-09 | Academic record/certificate correction policy unknown | High | High | Registrar policy workshop and immutable audit model | University registrar |
| R-10 | University approvals delay critical path | High | High | Decision SLA, escalation and recorded NO-GO | Delivery manager |
| R-11 | DR exercise fails 4h/24h targets | Medium | High | Early restoration rehearsal and runbook corrections | SRE |
| R-12 | Scope creep from unspecified payments/features | Medium | High | RTM gate and signed change request before new work | Product owner |

# 10. External dependencies — all 12 unchanged

# 10A. Integration and external dependency inventory

| ID | Dependency | Scope function | Evidence / contract required | RTM family | Current status |
| --- | --- | --- | --- | --- | --- |
| INT-01 | Digi-Pharmed / PRTS | OAuth2 SSO | University IdP sponsor, discovery metadata, client registration, scopes, sandbox users, signed claims | IAM / SEC | Blocked until contract and credentials verified |
| INT-02 | DigiLocker | Academic credentials | University DigiLocker onboarding, issuer registration, signed-document contract, callback and consent policy | ASM / SEC | Blocked until registration and signed artifact format |
| INT-03 | Live classroom provider | HD sessions, breakout/polls/whiteboard, recordings | Provider shortlist, seat/concurrency entitlement, API/webhook, India residency, retention | ACD / MOB / NFR | Blocked until provider capabilities and load evidence |
| INT-04 | CDN / DRM / media storage | AV delivery, protected offline cache | Object store, CDN edge, DRM license/key policy, transcoding and access tests | ACD / MOB / SEC | Blocked until architecture/security approval |
| INT-05 | Email service | Notifications | Sender/domain verification, quotas, callback and template policy | COM / OPS | Provider not selected |
| INT-06 | SMS gateway | OTP and alerts | Sender registration, rate limits, delivery receipts, country/India compliance | IAM / COM | Provider not selected |
| INT-07 | WhatsApp Business | Notifications | Business account, approved templates, opt-in/consent, callback signing | COM / SEC | Provider not selected |
| INT-08 | Mobile push | Android/iOS push | App identities, APNs/FCM configuration, device token lifecycle | MOB / COM | Developer accounts and provider access pending |
| INT-09 | AI question-generation provider | Draft questions, mandatory SME review | Model API contract, prompt/data policy, review state enforcement | ASM / SEC | Provider/data handling approval pending |
| INT-10 | Registrar signature service | Digitally signed certificates and marksheets | Signer authorization, key custody, signature verification, revocation/correction policy | ASM / SEC | Signing authority pending |
| INT-11 | Mobile distribution | Concurrent Android/iOS go-live | Store accounts, signing, privacy disclosure, build/release credentials | MOB / OPS | Account and release prerequisites pending |
| INT-12 | Independent VAPT provider | CERT-In empanelled assessment | Scope, assessor engagement, report and remediation verification | SEC / OPS | Booking and test scope pending |

# 11. Technical inventories preserved from prior design drafts

# 11A. All 38 candidate REST APIs

| ID | Method | Candidate path | Purpose | Owner | RTM | Critical control |
| --- | --- | --- | --- | --- | --- | --- |
| IAM-API-01 | POST | /api/v1/auth/otp/challenges | Initiate OTP challenge | IAM | IAM/SEC | OTP anti-abuse; no enumeration |
| IAM-API-02 | POST | /api/v1/auth/otp/verify | Verify OTP and issue session via approved IdP | IAM | IAM/SEC | Rate limit; replay prevention |
| IAM-API-03 | GET | /api/v1/me/permissions | Effective scoped permissions | IAM | IAM | No role escalation |
| IAM-API-04 | POST | /api/v1/role-assignments | Create scoped role assignment | IAM | IAM/SEC | Admin policy; audit |
| IAM-API-05 | GET | /api/v1/sso/callback | SSO callback (provider-dependent) | IAM | IAM | State/nonce validation |
| ORG-API-01 | GET | /api/v1/institutions | List authorized institutions | Organization | IAM/ACD | Tenant filter |
| ORG-API-02 | GET | /api/v1/programmes | Programme catalogue | Academic | ACD | Scope filter |
| ORG-API-03 | GET | /api/v1/programmes/{id}/periods | Year/semester hierarchy | Academic | ACD | Validated hierarchy |
| ORG-API-04 | GET | /api/v1/subjects/{id}/topics | Topic hierarchy | Academic | ACD | Validated hierarchy |
| CRS-API-01 | POST | /api/v1/courses | Create draft course | Content | ACD | Faculty authorization |
| CRS-API-02 | POST | /api/v1/courses/{id}/versions | Create content version | Content | ACD | Immutable published history |
| CRS-API-03 | POST | /api/v1/content/{id}/review | Submit or record review | Content | ACD | State transition audit |
| CRS-API-04 | POST | /api/v1/content/{id}/publish | Publish approved version | Content | ACD | Approval prerequisite |
| CRS-API-05 | GET | /api/v1/courses/{id}/prerequisites | Check prerequisite rules | Content | ACD | No circular dependency |
| LIVE-API-01 | POST | /api/v1/live-sessions | Schedule provider session | Live | ACD | Conflict detection |
| LIVE-API-02 | GET | /api/v1/live-sessions/{id}/join | Get authorized provider join info | Live | ACD | Scoped short-lived access |
| LIVE-API-03 | GET | /api/v1/recordings/{id} | Recording metadata and access | Media | ACD/MOB | DRM/entitlement |
| SRCH-API-01 | GET | /api/v1/library/search | Search titles/docs/transcripts | Search | ACD | Visibility filters |
| ASM-API-01 | POST | /api/v1/questions/generate | Request AI-assisted draft questions | Assessment | ASM | SME review required |
| ASM-API-02 | POST | /api/v1/questions/{id}/review | SME review decision | Assessment | ASM | Reviewer authorization |
| ASM-API-03 | POST | /api/v1/assessments/{id}/attempts | Start assessment attempt | Assessment | ASM | Eligibility/idempotency |
| ASM-API-04 | POST | /api/v1/attempts/{id}/submit | Submit answers | Assessment | ASM | Exactly one accepted finalization |
| ASM-API-05 | POST | /api/v1/attendance/sessions/{id}/records | Record attendance | Attendance | ASM | Duplicate protection |
| ASM-API-06 | POST | /api/v1/practical-logbook/entries | Add logbook entry | Assessment | ASM | Faculty validation pending |
| ASM-API-07 | GET | /api/v1/academic-records/{studentId} | Authorized lifetime academic history | Records | ASM | Student/privacy rules |
| ASM-API-08 | POST | /api/v1/marksheets/{id}/sign | Digitally sign marksheet | Credentials | ASM | Authorized signing |
| ASM-API-09 | POST | /api/v1/certificates/issue | Issue numbered signed QR certificate | Credentials | ASM | Registrar authority |
| ASM-API-10 | GET | /api/v1/certificates/verify/{code} | Verify certificate authenticity | Credentials | ASM/SEC | Minimized public disclosure |
| COM-API-01 | GET | /api/v1/dashboards/me | Role dashboard | Reporting | COM | Tenant scoped |
| COM-API-02 | POST | /api/v1/reports/queries | Run authorized report definition | Reporting | COM | No arbitrary SQL |
| COM-API-03 | POST | /api/v1/forums/{id}/posts | Create forum post | Communications | COM | Visibility/moderation pending |
| COM-API-04 | POST | /api/v1/announcements | Publish announcement | Communications | COM | Audience authorization |
| COM-API-05 | GET | /api/v1/calendar | Read calendar | Communications | COM | Role-scoped events |
| COM-API-06 | POST | /api/v1/notifications/requests | Queue templated notification | Notifications | COM | Recipient policy, idempotency |
| COM-API-07 | GET | /api/v1/notifications/{id}/status | Read delivery status | Notifications | COM | No cross-tenant leakage |
| MOB-API-01 | GET | /api/v1/mobile/sync-manifest | Fetch permitted offline sync metadata | Mobile | MOB | Device entitlements |
| MOB-API-02 | POST | /api/v1/mobile/sync-receipts | Acknowledge sync state | Mobile | MOB | Conflict rules pending |
| OPS-API-01 | GET | /health/ready | Internal readiness | Platform | OPS | Not public; no secrets |

# 11B. All 10 candidate events

| ID | Event (proposal) | Producer | Consumer | Illustrative payload | Safety rule |
| --- | --- | --- | --- | --- | --- |
| EV-01 | ContentPublished | Content | Search, analytics | contentId, version, tenantId | Outbox; projection rebuild |
| EV-02 | LiveSessionScheduled | Live | Calendar, notification | sessionId, start, providerRef | Avoid duplicate reminders |
| EV-03 | AttendanceRecorded | Attendance | Reporting, absence alerts | sessionId, learnerId, status | Idempotent alert evaluation |
| EV-04 | QuestionReviewed | Assessment | Assessment publication | questionId, reviewerDecision | Reject unapproved publication |
| EV-05 | AssessmentSubmitted | Assessment | Grade/academic record | attemptId, submittedAt | One final submission |
| EV-06 | GradeFinalized | Assessment | Academic records, reports | gradeId, version | No duplicate grade mutation |
| EV-07 | CertificateIssued | Credentials | DigiLocker, notification | certificateId, number | No duplicate issue |
| EV-08 | NotificationRequested | Notifications | Delivery adapters | notificationId, templateId | Retry + dedup + provider callback |
| EV-09 | MediaAssetReady | Media | Content/search projection | assetId, contentVersion | DRM/permission check |
| EV-10 | AuditEvidenceAnchored | Platform | Compliance storage | auditBatchId, integrityRef | Tamper evidence verification |

# 11C. Exactly six application roles

| Role | Source-described responsibility | Proposed least-privilege boundary | Authorization scope | Open approval |
| --- | --- | --- | --- | --- |
| University Super Admin | University-wide administration | Administration only within formally approved University tenant; sensitive changes require strong auth and audit | University / all institutions? | Exact privileges and cross-institution scope OPEN |
| SPC Admin | SPC administration | Scoped to explicitly assigned SPC jurisdiction and linked institutions | SPC / jurisdiction | SPC-to-institution cardinality OPEN |
| Institution Admin | Institution administration | Scoped to assigned institution, not automatically all SPC or University data | Institution | Whether one person may administer multiple institutions OPEN |
| Faculty/Educator | Teaching and course activities | Only courses/classes and learner records explicitly assigned | Course / institution | Course sharing and co-author review rights OPEN |
| Student/Learner | Learning and personal academic activities | Own enrollments, assessments, attendance, results and approved learning resources | Self / enrollment | Guardian, transfer, lifetime account mapping OPEN |
| Registered Pharmacist | Professional learning role | Only authorized pharmacist learning/credential features after identity verification | Self / verified professional identity | Exact differentiation from Student and professional verification OPEN |

# 11D. Candidate data objects — Part A

| Object ID | Candidate object | Attributes from Day 4 | Day 2 RTM |
| --- | --- | --- | --- |
| ORG-01 | University | university_id, display_name, status | IAM-001, IAM-016 |
| ORG-02 | SPC jurisdiction | spc_id, name, parent_reference | IAM-002, IAM-016 |
| ORG-03 | Institution | institution_id, name, organization_reference | IAM-003, IAM-016 |
| IAM-OBJ-01 | User identity | user_id, identity_provider_ref, status | IAM-007..015 |
| IAM-OBJ-02 | Role definition | role_id, role_code, role_name | IAM-001..008 |
| IAM-OBJ-03 | Permission | permission_id, resource, action | IAM-008, IAM-017 |
| IAM-OBJ-04 | Role–permission grant | role_id, permission_id, scope | IAM-008, IAM-017 |
| IAM-OBJ-05 | User membership/role assignment | user_id, organization_id, role_id, validity | IAM-007..008, IAM-016 |
| IAM-OBJ-06 | Provisioning/import batch | batch_id, initiator, outcome | IAM-018..020 |
| IAM-OBJ-07 | External SSO link | user_id, provider, subject_ref | IAM-015 |

# 11E. Candidate data objects — Part B

| Object ID | Candidate object | Attributes from Day 4 | Day 2 RTM |
| --- | --- | --- | --- |
| ACD-OBJ-01 | Programme | programme_id, name, status | ACD-001 |
| ACD-OBJ-02 | Year/Semester | period_id, programme_id, label | ACD-002 |
| ACD-OBJ-03 | Subject | subject_id, period_id, title | ACD-003 |
| ACD-OBJ-04 | Topic | topic_id, subject_id, title | ACD-004 |
| ACD-OBJ-05 | Course | course_id, academic_ref, status | ACD-005 |
| ACD-OBJ-06 | Course prerequisite | course_id, required_course_ref, rule | ACD-006 |
| ACD-OBJ-07 | Content item | content_id, course_ref, content_type | ACD-005, ACD-020 |
| ACD-OBJ-08 | Content version | content_id, version, approval_state | ACD-008..009 |
| ACD-OBJ-09 | Content contributor | content_id, user_id, contribution_role | ACD-007 |
| ACD-OBJ-10 | Content approval event | version_ref, actor, transition, timestamp | ACD-008..009 |
| ACD-OBJ-11 | Live class session | session_id, course_ref, provider_ref | ACD-010..015 |
| ACD-OBJ-12 | Class schedule | session_id, planned_time, resource_ref | ACD-018..019 |
| ACD-OBJ-13 | Recording / transcript metadata | session_id, asset_ref, transcript_ref | ACD-015..017 |
| ACD-OBJ-14 | Library index record | content_ref, title, searchable_text_ref | ACD-020..023 |

# 11F. Candidate data objects — Part C

| Object ID | Candidate object | Attributes from Day 4 | Day 2 RTM |
| --- | --- | --- | --- |
| ASM-OBJ-01 | Attendance record | session_ref, person_ref, status, time | ASM-001..004 |
| ASM-OBJ-02 | Absence notification trigger | attendance_ref, recipient_scope, status | ASM-002..004 |
| ASM-OBJ-03 | Question bank item | question_id, subject_ref, version, state | ASM-005 |
| ASM-OBJ-04 | AI question draft | draft_id, prompt_ref, reviewer_status | ASM-006..007 |
| ASM-OBJ-05 | SME review decision | draft_ref, reviewer_ref, decision, timestamp | ASM-007 |
| ASM-OBJ-06 | Assessment definition | assessment_id, chapter_ref, delivery_scope | ASM-008..009 |
| ASM-OBJ-07 | Assessment attempt / response | attempt_id, learner_ref, response_ref | ASM-008..011 |
| ASM-OBJ-08 | Grade / grading event | attempt_ref, grader_ref, score, event | ASM-010..011 |
| ASM-OBJ-09 | Assignment | assignment_id, course_ref, due_rule | ASM-012..013 |
| ASM-OBJ-10 | Assignment submission | assignment_ref, learner_ref, submission_ref | ASM-012..013 |
| ASM-OBJ-11 | Practical logbook entry | learner_ref, practical_ref, evidence_ref | ASM-014 |
| ASM-OBJ-12 | Marksheets | marksheet_id, learner_ref, signature_ref | ASM-015..016 |
| ASM-OBJ-13 | Lifetime academic record | learner_ref, record_ref, achievement_ref | ASM-017 |
| ASM-OBJ-14 | Certificate | certificate_id, unique_number, learner_ref | ASM-018..023 |
| ASM-OBJ-15 | Certificate verification | certificate_ref, verification_token, state | ASM-021..022 |
| ASM-OBJ-16 | Credential integration receipt | certificate_ref, provider_ref, result | ASM-023 |

# 11G. Candidate data objects — Part D

| Object ID | Candidate object | Attributes from Day 4 | Day 2 RTM |
| --- | --- | --- | --- |
| COM-OBJ-01 | Dashboard/report definition | report_id, owner_scope, specification | COM-001..009 |
| COM-OBJ-02 | Reporting projection | source_ref, metric_key, period, value | COM-006..009, COM-022 |
| COM-OBJ-03 | Forum / discussion item | thread_id, course_ref, author_ref | COM-010 |
| COM-OBJ-04 | Announcement | announcement_id, audience_scope, message | COM-011 |
| COM-OBJ-05 | Platform message | message_id, sender_ref, recipient_scope | COM-012 |
| COM-OBJ-06 | Academic calendar event | event_id, academic_scope, start_time | COM-013 |
| COM-OBJ-07 | Notification template | template_id, channel, version | COM-014..020 |
| COM-OBJ-08 | Notification request | request_id, event_ref, channel, status | COM-014..019 |
| COM-OBJ-09 | Delivery attempt/receipt | request_id, provider_ref, delivery_state | COM-021 |
| MOB-OBJ-01 | Playback/bookmark/notes | learner_ref, media_ref, position, note_ref | MOB-015..021 |
| MOB-OBJ-02 | Device notification preference | user_ref, channel, preference | MOB-023..025 |
| MOB-OBJ-03 | Offline cache manifest | device_ref, asset_ref, expiry | MOB-026 |
| SEC-OBJ-01 | Tamper-evident audit event | event_id, actor, action, integrity_ref | IAM-020, SEC-005..007, SEC-016 |
| OPS-OBJ-01 | Test / acceptance evidence | test_id, RTM_id, result, evidence_ref | OPS-005..010 |
| OPS-OBJ-02 | External integration transaction | integration_id, provider, correlation_ref, status | IAM-015, ASM-023, COM-018 |

# 12. Unresolved clarification and decision registers — verbatim carry-forward from Day 9

# 12A. All 22 Day 3 clarifications

| Clarification ID | Decision required (unchanged) | Proposed owner | Status |
| --- | --- | --- | --- |
| D3-CL-01 | University / SPC / Institution parent-child cardinalities and whether hierarchy can change | University sponsor | OPEN |
| D3-CL-02 | Whether one person may hold multiple roles and roles in multiple institutions | University IAM owner | OPEN |
| D3-CL-03 | Approved permission matrix per role and tenant, including pharmacist access | University IAM owner | OPEN |
| D3-CL-04 | Student enrolment ownership and transfer between institutions | Academic SME | OPEN |
| D3-CL-05 | Academic taxonomy reuse and relationship between Course and Programme/Subject/Topic | Academic SME | OPEN |
| D3-CL-06 | Prerequisite equivalence, overrides and cycle prevention | Academic SME | OPEN |
| D3-CL-07 | Content approver authority, publish/rollback, version immutability | Content SME | OPEN |
| D3-CL-08 | Live class attendance source, scheduling conflict rules, recording retention | Academic/IT SME | OPEN |
| D3-CL-09 | Question/SME reviewer authorization, AI data-sharing and audit expectations | Assessment SME | OPEN |
| D3-CL-10 | Assessment attempt, retake, grading, correction and result-release rules | Assessment SME | OPEN |
| D3-CL-11 | Lifetime record meaning, correction, archival and migration | Registrar | OPEN |
| D3-CL-12 | Certificate revocation/reissue, QR public data fields, signing authority | Registrar | OPEN |
| D3-CL-13 | Report metric definitions, MPR format, SLA calculations and data freshness | University reporting owner | OPEN |
| D3-CL-14 | Notification preference precedence, provider retries, retention and consent | University communications owner | OPEN |
| D3-CL-15 | Mobile offline scope, cache expiry, synchronization and conflict resolution | Mobile/product owner | OPEN |
| D3-CL-16 | Concurrency workload definition, API latency targets, content volumes | University technical owner | OPEN |
| D3-CL-17 | Provider contracts/sandbox credentials for SSO, live class, DigiLocker, messaging, DRM | Integration owners | OPEN |
| D3-CL-18 | Data classification, retention schedule (except explicit obligations), deletion and legal holds | University security/legal | OPEN |
| D3-CL-19 | Payment scope: title/service label exists, but no defined payment business workflow | University business owner | OPEN |
| D3-CL-20 | Formal approval of 120-working-day plan against source 12-week roadmap | University sponsor / PMO | OPEN |
| D3-CL-21 | Who approves ERD, schema changes and organization-scoped data access | University sponsor / architecture board | OPEN |
| D3-CL-22 | Role-specific data access and reporting for Registered Pharmacist | University business owner | OPEN |

# 12B. All 12 Day 5 decisions

| Decision ID | Question / decision (unchanged) | Status |
| --- | --- | --- |
| D5-DEC-01 | Select PostgreSQL deployment/version, extension policy and India regions | OPEN — approval required |
| D5-DEC-02 | Approve UUID/BIGINT primary key strategy per domain | OPEN — approval required |
| D5-DEC-03 | Approve tenant-scoping and RLS strategy after organizational cardinalities | OPEN — approval required |
| D5-DEC-04 | Approve schema/service ownership and cross-domain data exchange | OPEN — approval required |
| D5-DEC-05 | Approve academic/attendance/assessment uniqueness grains | OPEN — approval required |
| D5-DEC-06 | Approve record retention, legal holds and correction workflows | OPEN — approval required |
| D5-DEC-07 | Approve index/workload measurement and partition thresholds | OPEN — approval required |
| D5-DEC-08 | Approve schema migration tooling, release controls and DBA access | OPEN — approval required |
| D5-DEC-09 | Approve backup, PITR and geo-DR topology with measured drills | OPEN — approval required |
| D5-DEC-10 | Approve public certificate verification data disclosure policy | OPEN — approval required |
| D5-DEC-11 | Approve outbox/integration replay semantics | OPEN — approval required |
| D5-DEC-12 | Approve Day 5 physical baseline before implementation | OPEN — approval required |

# 12C. All 14 Day 6 decisions

| Decision ID | Open decision | Status |
| --- | --- | --- |
| D6-DEC-01 | Approve bounded context ownership and deployable service grouping | OPEN — no approval recorded |
| D6-DEC-02 | Approve OpenAPI versioning, compatibility and deprecation rules | OPEN — no approval recorded |
| D6-DEC-03 | Approve identity token flow, SSO callback and six-role resource authorization matrix | OPEN — no approval recorded |
| D6-DEC-04 | Approve OTP/MFA/session semantics and anti-abuse controls | OPEN — no approval recorded |
| D6-DEC-05 | Approve state transitions and approval owners for course publishing | OPEN — no approval recorded |
| D6-DEC-06 | Approve live-class provider contracts, calendar conflict and webhook rules | OPEN — no approval recorded |
| D6-DEC-07 | Approve question SME-review and assessment/attendance business idempotency | OPEN — no approval recorded |
| D6-DEC-08 | Approve certificate signing, DigiLocker handoff, correction and disclosure rules | OPEN — no approval recorded |
| D6-DEC-09 | Approve notification channel adapters, retry windows and templates | OPEN — no approval recorded |
| D6-DEC-10 | Approve event delivery semantics, outbox ownership and retention | OPEN — no approval recorded |
| D6-DEC-11 | Approve mobile offline synchronization and DRM authorization | OPEN — no approval recorded |
| D6-DEC-12 | Approve 500k-user workload, rate limits, SLOs and contract-test gates | OPEN — no approval recorded |
| D6-DEC-13 | Approve data residency and VAPT scope across external providers | OPEN — no approval recorded |
| D6-DEC-14 | Approve API security/privacy review and contract sign-off process | OPEN — no approval recorded |

# 12D. All 12 Day 7 decisions

| Decision ID | Decision / required owner | Status |
| --- | --- | --- |
| D7-DEC-01 | Approve six-role permission matrix by action and resource scope | OPEN — not approved |
| D7-DEC-02 | Resolve University/SPC/institution hierarchy and cross-tenant exception policy | OPEN — not approved |
| D7-DEC-03 | Confirm multi-role membership, delegation, session scope and role revocation | OPEN — not approved |
| D7-DEC-04 | Approve Registrar signing authority without inventing seventh role | OPEN — not approved |
| D7-DEC-05 | Approve SSO token mapping, OTP/MFA flows and session lifecycle | OPEN — not approved |
| D7-DEC-06 | Approve service-to-service trust, broker ACL and callback verification | OPEN — not approved |
| D7-DEC-07 | Approve provider inventory, contracts, sandboxes and India residency evidence | OPEN — not approved |
| D7-DEC-08 | Approve media DRM, recording entitlement and offline revocation rules | OPEN — not approved |
| D7-DEC-09 | Approve public QR verifier minimal response and anti-abuse rules | OPEN — not approved |
| D7-DEC-10 | Approve notification channel consent, templates and retry policy | OPEN — not approved |
| D7-DEC-11 | Approve security acceptance test evidence, VAPT and remediation gate | OPEN — not approved |
| D7-DEC-12 | Approve Day 7 authorization and integration contract baseline | OPEN — not approved |

# 12E. All 14 Day 8 decisions

| ID | Decision | State |
| --- | --- | --- |
| D8-DEC-01 | Approve integration owners, provider inventory and sandbox access | OPEN — approval required |
| D8-DEC-02 | Approve exact SSO/Digi-Pharmed/PRTS identity mapping and trust contracts | OPEN — approval required |
| D8-DEC-03 | Approve DigiLocker onboarding, Registrar signing and certificate disclosures | OPEN — approval required |
| D8-DEC-04 | Approve live-class/recording provider and concurrency entitlements | OPEN — approval required |
| D8-DEC-05 | Approve DRM/CDN/media residency and offline revocation behavior | OPEN — approval required |
| D8-DEC-06 | Approve messaging providers, consent, templates and rate quotas | OPEN — approval required |
| D8-DEC-07 | Approve AI question-generation data handling and SME review contract | OPEN — approval required |
| D8-DEC-08 | Approve end-to-end sequence and failure handling contracts | OPEN — approval required |
| D8-DEC-09 | Approve 500k concurrency interpretation and workload profile | OPEN — approval required |
| D8-DEC-10 | Approve p95/p99, TPS, soak duration and error thresholds (not in source) | OPEN — approval required |
| D8-DEC-11 | Approve India residency, audit retention and DR evidence methods | OPEN — approval required |
| D8-DEC-12 | Approve integration harness and synthetic data policies | OPEN — approval required |
| D8-DEC-13 | Approve CERT-In VAPT engagement, remediation and mobile security gate | OPEN — approval required |
| D8-DEC-14 | Approve Day 8 baseline and Day 9 transition | OPEN — approval required |

# 12F. All 12 Day 9 decisions

| Decision ID | Required approval | Status |
| --- | --- | --- |
| D9-DEC-01 | Approve 120-day stage allocations, gates and acceptance owners | OPEN — not approved |
| D9-DEC-02 | Approve baseline calendar, working-day definition, holidays and start date | OPEN — not approved |
| D9-DEC-03 | Approve detailed WBS, RTM mapping and scope exclusions | OPEN — not approved |
| D9-DEC-04 | Approve team availability, role mix, ramp-up and budget | OPEN — not approved |
| D9-DEC-05 | Approve three-point effort estimates, risk reserves and contingency | OPEN — not approved |
| D9-DEC-06 | Approve provider procurement, onboarding lead times and contractual SLAs | OPEN — not approved |
| D9-DEC-07 | Approve true CPM network after precedence and durations are supplied | OPEN — not approved |
| D9-DEC-08 | Approve 500k workload model and measurable NFR acceptance thresholds | OPEN — not approved |
| D9-DEC-09 | Approve VAPT, DR, UAT and mobile-store lead-time reservations | OPEN — not approved |
| D9-DEC-10 | Approve risk appetite, escalation thresholds and decision SLAs | OPEN — not approved |
| D9-DEC-11 | Approve Day 10 scope/design readiness pack inputs | OPEN — not approved |
| D9-DEC-12 | Authorize or withhold transition beyond discovery gate | OPEN — not approved |

# 13. Day 10 gate decisions — newly proposed

| ID | Decision required | State |
| --- | --- | --- |
| D10-DEC-01 | Accept Day 2 original RTM as controlled reference after atomic wording audit | OPEN — not approved |
| D10-DEC-02 | Approve or reject critical tenancy and role assumptions | OPEN — not approved |
| D10-DEC-03 | Approve clarification ownership and resolution dates | OPEN — not approved |
| D10-DEC-04 | Approve provider dependency plan and fallback decisions | OPEN — not approved |
| D10-DEC-05 | Approve source-defined and proposed NFR acceptance measures separately | OPEN — not approved |
| D10-DEC-06 | Approve architecture traceability and security gate criteria | OPEN — not approved |
| D10-DEC-07 | Approve staffing/estimation assumptions and risk contingencies | OPEN — not approved |
| D10-DEC-08 | Decide G-D10: GO, CONDITIONAL GO or NO-GO with evidence | OPEN — not approved |
| D10-DEC-09 | Approve next-phase authority and exclusions | OPEN — not approved |
| D10-DEC-10 | Approve baseline versioning and PR review controls | OPEN — not approved |

# 14. Controlled artifact and evidence register

| Artifact | Required baseline status | Evidence / repository expectation |
| --- | --- | --- |
| Day 1 Discovery and scope | Original text preserved; approval status explicit | Word file + source reference |
| Day 2 atomic RTM | 152 original IDs and wording; independent audit pending | Word/RTM export + checksum |
| Day 3 logical objects | 55 candidate objects; 22 questions open | Data catalogue + clarifications |
| Day 4 logical ERD | Candidate relationships only | ERD review notes |
| Day 5 physical schema | Proposed; no migration executed | Schema/decision review |
| Day 6 API/events | 38 candidate APIs, 10 candidate events | Contract inventory and version |
| Day 7 IAM/threat model | Six-role policy draft; security approval pending | Policy and threat model |
| Day 8 integrations/NFR | 12 external dependencies, acceptance proposals | Provider evidence and NFR plan |
| Day 9 WBS/estimate | 120-day proposal; 18 WPs; staffing illustrative | Estimate and dependency evidence |
| Day 10 gate report | NOT APPROVED pending sign-off | Decision minutes, reviewer signatures and links |

# 15. Day 10 closure actions and Day 11 handoff

University business owner: validate atomic requirement wording and confirm scope exclusions and open questions.

Architecture/data leads: obtain cardinality, role, data ownership, API/event and migration decisions; update designs only through reviewed changes.

Integration/security leads: secure vendor contracts, IdP/Registrar authority, residency and VAPT commitments.

Delivery/QA leads: baseline measurable acceptance, detailed estimates, staffing, critical path and test evidence owners.

Day 11 proposed next step: commence detailed design only for approved/unblocked areas after recorded G-D10 decision. No implementation authorization is implied.

# 16. Formal review and approval record

| Reviewer / authority | Decision | Signature / date / evidence |
| --- | --- | --- |
| University Sponsor / Product Owner | PENDING | — |
| Business Analyst / RTM Custodian | PENDING | — |
| Solution Architect | PENDING | — |
| Data Architect | PENDING | — |
| IAM / Security & Privacy Lead | PENDING | — |
| Integration Lead | PENDING | — |
| QA / Performance Lead | PENDING | — |
| Delivery Manager | PENDING | — |