# UNIVERSITY LMS

DAY 14 — ENVIRONMENT CONFIGURATION, CI/CD QUALITY GATES, DEPLOYMENT VERIFICATION & OPERATIONAL ACCEPTANCE

Draft v0.1 | Design-only continuation | 120-working-day delivery | Day 10 NO-GO remains in force

| Document control | Baseline / rule |
| --- | --- |
| Primary traceability | Original Day 2 atomic RTM: 152 IDs in eight families; no IDs added, removed or renumbered |
| Previous inputs | Day 3: 55 candidate objects / 22 clarifications; Day 6: 38 candidate APIs / 10 events; Days 10–13 design and gate records |
| Day 14 purpose | Turn Day 13 pipeline and environment proposals into testable configuration standards, release quality gates and operational acceptance evidence |
| Approval state | DRAFT / NOT APPROVED. No infrastructure, pipeline, production migration or deployment is authorized |
| Scope controls | Six source roles only; no inferred payment workflows, new providers or RAG functionality |

# 1. Objectives and non-negotiable constraints

Define environment-specific configuration profiles and promotion boundaries for development, integration, QA, performance, staging, production and disaster recovery.

Create enforceable candidate CI/CD quality gates with explicit evidence, ownership, failure conditions, exceptions and rollback rules.

Specify safe deployment verification for APIs, database migrations, events, mobile releases and media/provider integrations.

Define operational acceptance and SRE handover criteria against source NFRs: ≥500,000 concurrent users, ≥99.5% O&M availability, RTO ≤4h, RPO ≤24h, India residency, ≥5-year tamper-evident audit.

Carry forward all outstanding Day 3–13 decisions; treat technical choices and numeric quality thresholds not in the source as proposed, not approved.

# 2. Day 2 requirements family coverage — original 152 unchanged

| Family | Requirement IDs | Count | Day 6 design coverage |
| --- | --- | --- | --- |
| NFR | NFR-001–010 | 10 | Scale, reliability, latency evidence, DR |
| IAM | IAM-001–020 | 20 | Login, MFA, scoped RBAC, SSO, identities |
| ACD | ACD-001–023 | 23 | Academic taxonomy, course, publishing, classes, media/search |
| ASM | ASM-001–023 | 23 | Attendance, AI+SME, assessment, marksheets, records, certificates |
| COM | COM-001–022 | 22 | Dashboards, MPR, forums, calendar, notification channels |
| MOB | MOB-001–028 | 28 | Web/mobile parity, DRM, offline and device security |
| SEC | SEC-001–016 | 16 | OWASP, audit, India residency, VAPT, authz |
| OPS | OPS-001–010 | 10 | Monitoring, deployment, backups, DR, operations |

# 3. Day 13 environment inventory — carried forward unchanged

| Environment | Purpose | Isolation & access proposal | Promotion gate |
| --- | --- | --- | --- |
| Developer / disposable | Local unit tests, mock providers, synthetic data | No production credentials or personal data; disposable databases and mocks | Automated tests |
| Shared integration | API, event, schema and provider-sandbox integration | Separate service identities, controlled outbound egress, nonproduction test data | Contract and integration test evidence |
| QA / system | Cross-role and multi-tenant E2E validation | Representative synthetic institutions, learners, records and entitlements | Functional/security test pass |
| Performance / resilience | 500k concurrency workload rehearsal, failover and recovery | Isolated capacity; realistic anonymized/synthetic dataset; provider quotas approved | Measured performance and DR evidence |
| Preproduction / UAT | University review and release candidate sign-off | Production-like config with no uncontrolled production PII | University acceptance and VAPT clearance |
| Production / O&M | University services, ≥99.5% availability target | Private data network, India residency, tightly restricted change rights | Explicit go-live approval |
| Geo-DR | RTO ≤4h, RPO ≤24h restoration | Approved India-resident recovery region, independent secrets and backups | Timed DR drill |

# 4. Configuration catalogue and separation of duties

| Configuration class | Environment-specific policy proposal | Verification evidence | Decision owner |
| --- | --- | --- | --- |
| Application settings | Typed, schema-validated config; defaults safe; version-controlled non-secret values | Config schema validation; environment diff | Architecture / DevOps |
| Secrets | Secrets manager references only; no values in GitHub, artifacts or logs | Secret scan; rotation drill | Security |
| Identity / SSO | Per-environment client ID, redirect URI, audience, issuer, test IdP | OIDC callback negative tests | IAM owner |
| Database | Dedicated role/connection, migration account separate from app role | Least-privilege DB audit | DBA |
| Tenant boundaries | Explicit institution/SPC context and policy, deny-by-default | Cross-tenant tests | Security / Product |
| Queues and events | Environment-specific topics, DLQ, schema versions and replay controls | Contract and replay tests | Integration lead |
| Media / CDN | Separate buckets, DRM keys, signed URL policies and origin restrictions | Access and expiry tests | Media lead |
| Notifications | Sandbox-only senders and recipient allowlists outside production | No real recipient test | Communications owner |
| AI question generation | Test API credentials and masked data; human SME review enforced | Workflow test | Assessment owner |
| Feature flags | Explicit owner, expiry, rollback and safe default; no bypass of authorization | Flag lifecycle test | Product / SRE |
| Telemetry | Redaction, retention, trace correlation, environment labels | PII leak and audit checks | Security / SRE |
| DR | Restore endpoints and key custody independent of primary where feasible | Failover rehearsal | SRE / Security |

# 5. Environment promotion policy and evidence package

| Promotion | Entry criteria | Required approvals | Reject / rollback condition |
| --- | --- | --- | --- |
| Local → Integration | Unit tests, lint, dependency scan, contract lint, schema check | Engineering peer review | Failed deterministic tests |
| Integration → QA | API/event contract tests, DB migration rehearsal, negative auth tests | Tech lead + QA | Unresolved high-risk regression |
| QA → Performance | Functional acceptance, anonymized data, capacity workload definition | QA + performance lead | Unknown load mix or missing environment parity |
| Performance → Staging | 500k-user evidence and approved SLO/NFR interpretation, recovery plan | Architecture + SRE + Security | Load or security gate fails |
| Staging → Production | Signed UAT, CERT-In VAPT, DR drill, mobile parity, change ticket | University PO + Security + Ops | Missing approvals / evidence |
| Production → DR exercise | Backups, recovery permissions, runbook, validation plan | Incident / DR authority | Data-integrity mismatch |

# 6. CI/CD quality gates — proposal, not a configured pipeline

| Gate | Automated or manual control | Minimum evidence | Failure response |
| --- | --- | --- | --- |
| QG-01 Source integrity | Branch protection/PR, reviewer, signed or attributable commit | PR and review log | Block merge |
| QG-02 Static quality | Format/lint, type check, unit tests and coverage policy | Machine-readable reports | Fail build |
| QG-03 Dependencies | SCA/license, SBOM, pinned dependencies | SBOM and severity report | Block per approved severity policy |
| QG-04 Secret protection | Secret scan and IaC static analysis | Scan results | Block / rotate exposed secret |
| QG-05 API compatibility | OpenAPI lint and consumer/provider contract tests | Schema compatibility report | Reject breaking change |
| QG-06 Database safety | Migration checksum, rehearsal, schema diff, rollback plan | DB migration dry-run | Block promotion |
| QG-07 IAM isolation | Six-role matrix and negative authorization tests | BOLA/BFLA evidence | Block release |
| QG-08 Security validation | DAST, OWASP, mobile MASVS, VAPT evidence | Risk disposition / remediation | Block per signed security policy |
| QG-09 Performance | Agreed concurrency workload, p95/p99, error rates, saturation | Load report and sign-off | Block until targets met |
| QG-10 Recovery | Restore and geo-DR exercise measured vs source targets | RTO/RPO and integrity report | Block production readiness |
| QG-11 Compliance | India residency, audit ≥5 years, retention and privacy controls | Review checklist | Block without compliance sign-off |
| QG-12 Release approval | Change record, deploy manifest, mobile go-live parity, rollback readiness | Signed release checklist | No production promotion |

# 7. Deployment automation verification — by component

| Component | Safe verification sequence | Rollback / compensation | Non-negotiable evidence |
| --- | --- | --- | --- |
| Web / API | Deploy candidate → health/readiness → synthetic login/course/assessment → traffic shift | Revert application version; preserve backward compatible DB | Version, build ID, checks, change ticket |
| Database | Backup/PITR point → additive migration → constraint checks → smoke → release | Roll forward / restore by approved plan; no assumed down migration | Migration checksum, data counts, recovery rehearsal |
| Event consumers | Schema check → staged consumer → replay and DLQ → cutover | Pause/revert consumer; reconcile events | Duplicate and out-of-order evidence |
| Search projection | Build new index → reconcile → alias switch | Alias back and replay | Index lag and record counts |
| Media / DRM | Protected upload → transcode → signed access → entitlement expiry | Revoke URLs/licenses; restore prior policy | Access, privacy and provider quota tests |
| Mobile | Device/version matrix → signed build → staged release → parity test | Store rollback policy / kill switch where supported | Android 8+, iOS 14+, security tests |
| Notifications | Sandbox allowlist → template validation → delivery receipts → production approval | Disable channel and reconcile queue | Consent, sender registration, retries |
| Identity | Approved IdP client config → OIDC/OTP/MFA tests → controlled promotion | Restore prior config without weakening auth | Issuer, audience, MFA, session tests |

# 8. Release configuration and rollback decision tree

Before release: confirm approved change ID, immutable artifact digest, environment inventory, database compatibility window, backup validity and named release commander.

If predeployment gate fails: do not deploy. If deployment smoke fails: stop traffic promotion and invoke component-specific rollback.

If a database migration is not safely reversible: preserve compatible application version and use approved forward fix or PITR restoration decision; never automatically drop columns or academic records.

If an external provider fails: follow agreed circuit-breaker, retry and reconciliation policy; do not mark business operations successful without evidence.

For security incident or tenant leakage: immediately halt promotion, contain credentials/tokens and initiate incident response; preserve tamper-evident logs.

For mobile release: coordinate Android/iOS concurrent go-live with provider store review realities; PWA fallback is source-required and needs separate validation.

# 9. Operational acceptance criteria and source-versus-proposal distinction

| Acceptance dimension | Source-defined criterion | Verification / open definition | State |
| --- | --- | --- | --- |
| Concurrency | ≥500,000 concurrent users | Approve session/request definition, traffic mix, media vs API concurrency and load duration | NOT TESTED |
| Availability | ≥99.5% O&M uptime | Approve monitoring period, excluded maintenance, service-level indicators | NOT MEASURED |
| Disaster recovery | RTO ≤4 hours; RPO ≤24 hours | Time failover and data integrity in geo-DR rehearsal | NOT TESTED |
| Media delivery | CDN-backed AV across India | Regional playback, buffering and access rights; numeric media targets pending | NOT TESTED |
| Data residency | India data residency | Verify storage, backups, DR, CDN, IdP, logs and providers | NOT VERIFIED |
| Audit | Tamper-evident audit ≥5 years | Integrity, retention and retrieval tests | NOT VERIFIED |
| Academic records | Lifetime academic record | Preservation and correction/recovery procedures | NOT VERIFIED |
| Mobile | Android 8+, iOS 14+, parity, concurrent go-live, PWA fallback | Device matrix and app-store readiness | NOT TESTED |
| Security | OWASP Top 10, MASVS, CERT-In VAPT pre-go-live and annually | Assessment report and closure of findings | NOT DONE |
| Response time / error budget | No numeric source target | Propose thresholds only after University sign-off | OPEN |

# 10. Evidence and audit chain

| Evidence ID | Artifact | Minimum metadata | Owner |
| --- | --- | --- | --- |
| EV-14-01 | Environment inventory / configuration diff | Env, commit, owner, time, redacted values | DevOps |
| EV-14-02 | CI pipeline execution | Commit SHA, run ID, stage results, artifact digest | Engineering |
| EV-14-03 | Security and dependency reports | Tool/version, finding severity, disposition | Security |
| EV-14-04 | API and event contract report | Contract version, provider, consumer, compatibility | Integration |
| EV-14-05 | Migration rehearsal and rollback | Migration ID, row counts, checksum, recovery steps | DBA |
| EV-14-06 | Role/tenant authorization suite | Role, resource, tenant, positive/negative outcomes | QA / IAM |
| EV-14-07 | Load and capacity evidence | Workload mix, concurrency, latency, errors, saturation | Performance |
| EV-14-08 | DR and backup drill | RTO, RPO, integrity, operator and timestamp | SRE |
| EV-14-09 | Independent VAPT | Assessor, scope, findings and remediation sign-off | Security |
| EV-14-10 | Production change approval | Decision, authorized approvers, release notes, backout | Delivery / University |

# 11. Day 14 verification scenarios

| Test ID | Verification scenario | RTM family |
| --- | --- | --- |
| D14-T01 | Secret accidentally committed is detected before merge | SEC / OPS |
| D14-T02 | Development credentials cannot reach production | SEC / OPS |
| D14-T03 | Cross-tenant API and DB policy denied across all six roles | IAM / SEC |
| D14-T04 | Admin MFA enforced in every environment | IAM / SEC |
| D14-T05 | Breaking OpenAPI contract blocks promotion | OPS |
| D14-T06 | Incompatible event schema blocks consumer release | OPS |
| D14-T07 | DB migration rehearsal detects destructive change | OPS / ASM |
| D14-T08 | Restore preserves academic history and certificate integrity | ASM / NFR |
| D14-T09 | Notification sandbox cannot send to real learner | COM / SEC |
| D14-T10 | AI-generated question cannot publish without SME review | ASM |
| D14-T11 | CDN/DRM denies expired or unauthorized content | ACD / MOB |
| D14-T12 | Audit retention/integrity verifies ≥5 years policy | SEC |
| D14-T13 | Production deployment blocked without University approval | OPS |
| D14-T14 | Load test uses agreed 500k-user workload definition | NFR |
| D14-T15 | Availability instrumentation supports ≥99.5% O&M verification | NFR |
| D14-T16 | Geo-DR drill measures RTO ≤4h and RPO ≤24h | NFR / OPS |
| D14-T17 | Android 8+/iOS 14+ release parity test passes | MOB |
| D14-T18 | Provider timeout yields bounded retries and reconciliation | COM / OPS |
| D14-T19 | No secrets or personal data appear in build logs | SEC |
| D14-T20 | CERT-In VAPT and remediation sign-off gate release | SEC |
| D14-T21 | Deployment rollback preserves compatible database schema | OPS |
| D14-T22 | India residency verified for all storage and provider paths | SEC / NFR |
| D14-T23 | Disallowed role assignment is denied and audited | IAM |
| D14-T24 | Change evidence maps to original RTM ID and approved PR | OPS |

# 12. Day 14 decisions — open, not approved

| Decision ID | Decision | State |
| --- | --- | --- |
| D14-DEC-01 | Approve environment topology and configuration ownership | OPEN — approval required |
| D14-DEC-02 | Approve approved configuration schema and secret management mechanism | OPEN — approval required |
| D14-DEC-03 | Approve CI/CD platform, build isolation and artifact provenance | OPEN — approval required |
| D14-DEC-04 | Approve quality gate severity thresholds and exception workflow | OPEN — approval required |
| D14-DEC-05 | Approve branch protection and human PR review enforcement | OPEN — approval required |
| D14-DEC-06 | Approve database migration rehearsal, PITR and rollback policy | OPEN — approval required |
| D14-DEC-07 | Approve event contract compatibility and replay gates | OPEN — approval required |
| D14-DEC-08 | Approve release strategy for web, APIs, mobile and provider adapters | OPEN — approval required |
| D14-DEC-09 | Approve source NFR measurement methods and proposed numeric SLIs | OPEN — approval required |
| D14-DEC-10 | Approve audit evidence retention, access and India residency controls | OPEN — approval required |
| D14-DEC-11 | Approve independent VAPT release gate and remediation owners | OPEN — approval required |
| D14-DEC-12 | Approve release commander, separation of duties and incident escalation | OPEN — approval required |
| D14-DEC-13 | Approve 500k concurrency workload and performance environment parity | OPEN — approval required |
| D14-DEC-14 | Approve Day 14 baseline only after Day 10 gate closure | OPEN — approval required |

# 13. Day 13 design decisions — all 12 unchanged

| Decision ID | Required decision | Status |
| --- | --- | --- |
| D13-DEC-01 | Select IaC tool, provider and state-management architecture | OPEN — not approved |
| D13-DEC-02 | Approve account/project and environment isolation model | OPEN — not approved |
| D13-DEC-03 | Approve India-region selection and geo-DR boundaries | OPEN — not approved |
| D13-DEC-04 | Approve branch rules, PR reviewers and Word-document approval method | OPEN — not approved |
| D13-DEC-05 | Approve CI/CD platform, runner security and artifact registry | OPEN — not approved |
| D13-DEC-06 | Approve build provenance, SBOM, scanning thresholds and exceptions | OPEN — not approved |
| D13-DEC-07 | Approve application and database promotion/rollback strategies | OPEN — not approved |
| D13-DEC-08 | Approve mobile store release and web/mobile parity gate | OPEN — not approved |
| D13-DEC-09 | Approve security/IAM and production secrets custody | OPEN — not approved |
| D13-DEC-10 | Approve observability/SLO and incident/change governance | OPEN — not approved |
| D13-DEC-11 | Approve performance, DR and VAPT evidence acceptance criteria | OPEN — not approved |
| D13-DEC-12 | Approve Day 13 design after Day 10 blocking gate resolution | OPEN — not approved |

# 14. Day 13 unresolved blockers — unchanged

| Blocker | Consequence if unresolved | Closure evidence | Owner (proposed) |
| --- | --- | --- | --- |
| BLK-01 Organization/SPC/institution cardinality | Wrong tenancy and permissions | Signed hierarchy and assignment examples | University PO / IAM |
| BLK-02 Role scope and Registrar authority | Unauthorized grades/certificates | Approved role matrix and signer trust model | University security / Registrar |
| BLK-03 Source-level atomic RTM audit | Missing or invented acceptance criteria | Reviewed clause-to-ID-to-test mapping | Business analyst / QA |
| BLK-04 Integration vendors and credentials | Untestable API and release blockers | Provider contract, sandbox, quota and security acceptance | Integration lead |
| BLK-05 Concurrency workload definition | Invalid capacity design and budget | Peak scenarios, TPS, session model and sign-off | Performance lead |
| BLK-06 Data retention/correction/residency | Compliance and recovery risk | Policy, region map, data flow and deletion rules | Security/privacy |
| BLK-07 Estimation and staffing | Unreliable 120-day commitment | Bottom-up WBS, 26 FTE assumption validation | Delivery manager |
| BLK-08 Mobile/live-provider dependencies | Go-live and parity risk | App-store accounts, DRM, live vendor capacity | Mobile lead |
| BLK-09 Formal review sign-offs | Uncontrolled scope/architecture baseline | Signed gate record and decision log | University sponsor |

# 15. Day 13 gate criteria — unchanged

| Gate criterion | Pass evidence | Disposition |
| --- | --- | --- |
| G-D10-01 Source scope integrity | Original source + RTM + gap report reviewed | OPEN |
| G-D10-02 Clarification ownership | All open questions assigned and critical blockers resolved or explicitly risk-accepted | OPEN |
| G-D10-03 Architecture traceability | ERD, data dictionary, API/event inventories and decisions linked to IDs | OPEN |
| G-D10-04 IAM and security | Role matrix, threat review, residency/audit policy and VAPT plan accepted | OPEN |
| G-D10-05 Integration feasibility | Provider contracts, sandbox readiness and alternatives documented | OPEN |
| G-D10-06 NFR testability | 500k workload, availability, DR and mobile acceptance metrics signed | OPEN |
| G-D10-07 Delivery feasibility | Bottom-up estimation, resources, milestones and risks approved | OPEN |
| G-D10-08 Change control | Approved versioned baseline and exception process | OPEN |
| G-D10-09 Decision authority | Signed review minutes and approval record | OPEN |

# 16. Day 6 REST contracts — all 38 preserved

| ID | Method | Candidate path | Purpose | Owner | RTM | Critical control |
| --- | --- | --- | --- | --- | --- | --- |
| IAM-API-01 | POST | /api/v1/auth/otp/challenges | Initiate OTP challenge | IAM | IAM/SEC | OTP anti-abuse; no enumeration |
| IAM-API-02 | POST | /api/v1/auth/otp/verify | Verify OTP and issue session via approved IdP | IAM | IAM/SEC | Rate limit; replay prevention |
| IAM-API-03 | GET | /api/v1/me/permissions | Effective scoped permissions | IAM | IAM | No role escalation |
| IAM-API-04 | POST | /api/v1/role-assignments | Create scoped role assignment | IAM | IAM/SEC | Admin policy; audit |
| IAM-API-05 | GET | /api/v1/sso/callback | SSO callback (provider-dependent) | IAM | IAM | State/nonce validation |
| ORG-API-01 | GET | /api/v1/institutions | List authorized institutions | Organization | IAM/ACD | Tenant filter |
| ORG-API-02 | GET | /api/v1/programmes | Programme catalogue | Academic | ACD | Scope filter |
| ORG-API-03 | GET | /api/v1/programmes/{id}/periods | Year/semester hierarchy | Academic | ACD | Validated hierarchy |
| ORG-API-04 | GET | /api/v1/subjects/{id}/topics | Topic hierarchy | Academic | ACD | Validated hierarchy |
| CRS-API-01 | POST | /api/v1/courses | Create draft course | Content | ACD | Faculty authorization |
| CRS-API-02 | POST | /api/v1/courses/{id}/versions | Create content version | Content | ACD | Immutable published history |
| CRS-API-03 | POST | /api/v1/content/{id}/review | Submit or record review | Content | ACD | State transition audit |
| CRS-API-04 | POST | /api/v1/content/{id}/publish | Publish approved version | Content | ACD | Approval prerequisite |
| CRS-API-05 | GET | /api/v1/courses/{id}/prerequisites | Check prerequisite rules | Content | ACD | No circular dependency |
| LIVE-API-01 | POST | /api/v1/live-sessions | Schedule provider session | Live | ACD | Conflict detection |
| LIVE-API-02 | GET | /api/v1/live-sessions/{id}/join | Get authorized provider join info | Live | ACD | Scoped short-lived access |
| LIVE-API-03 | GET | /api/v1/recordings/{id} | Recording metadata and access | Media | ACD/MOB | DRM/entitlement |
| SRCH-API-01 | GET | /api/v1/library/search | Search titles/docs/transcripts | Search | ACD | Visibility filters |
| ASM-API-01 | POST | /api/v1/questions/generate | Request AI-assisted draft questions | Assessment | ASM | SME review required |
| ASM-API-02 | POST | /api/v1/questions/{id}/review | SME review decision | Assessment | ASM | Reviewer authorization |
| ASM-API-03 | POST | /api/v1/assessments/{id}/attempts | Start assessment attempt | Assessment | ASM | Eligibility/idempotency |
| ASM-API-04 | POST | /api/v1/attempts/{id}/submit | Submit answers | Assessment | ASM | Exactly one accepted finalization |
| ASM-API-05 | POST | /api/v1/attendance/sessions/{id}/records | Record attendance | Attendance | ASM | Duplicate protection |
| ASM-API-06 | POST | /api/v1/practical-logbook/entries | Add logbook entry | Assessment | ASM | Faculty validation pending |
| ASM-API-07 | GET | /api/v1/academic-records/{studentId} | Authorized lifetime academic history | Records | ASM | Student/privacy rules |
| ASM-API-08 | POST | /api/v1/marksheets/{id}/sign | Digitally sign marksheet | Credentials | ASM | Authorized signing |
| ASM-API-09 | POST | /api/v1/certificates/issue | Issue numbered signed QR certificate | Credentials | ASM | Registrar authority |
| ASM-API-10 | GET | /api/v1/certificates/verify/{code} | Verify certificate authenticity | Credentials | ASM/SEC | Minimized public disclosure |
| COM-API-01 | GET | /api/v1/dashboards/me | Role dashboard | Reporting | COM | Tenant scoped |
| COM-API-02 | POST | /api/v1/reports/queries | Run authorized report definition | Reporting | COM | No arbitrary SQL |
| COM-API-03 | POST | /api/v1/forums/{id}/posts | Create forum post | Communications | COM | Visibility/moderation pending |
| COM-API-04 | POST | /api/v1/announcements | Publish announcement | Communications | COM | Audience authorization |
| COM-API-05 | GET | /api/v1/calendar | Read calendar | Communications | COM | Role-scoped events |
| COM-API-06 | POST | /api/v1/notifications/requests | Queue templated notification | Notifications | COM | Recipient policy, idempotency |
| COM-API-07 | GET | /api/v1/notifications/{id}/status | Read delivery status | Notifications | COM | No cross-tenant leakage |
| MOB-API-01 | GET | /api/v1/mobile/sync-manifest | Fetch permitted offline sync metadata | Mobile | MOB | Device entitlements |
| MOB-API-02 | POST | /api/v1/mobile/sync-receipts | Acknowledge sync state | Mobile | MOB | Conflict rules pending |
| OPS-API-01 | GET | /health/ready | Internal readiness | Platform | OPS | Not public; no secrets |

# 17. Day 6 events — all 10 preserved

| ID | Event (proposal) | Producer | Consumer | Illustrative payload | Safety rule |
| --- | --- | --- | --- | --- | --- |
| EV-01 | ContentPublished | Content | Search, analytics | contentId, version, tenantId | Outbox; projection rebuild |
| EV-02 | LiveSessionScheduled | Live | Calendar, notification | sessionId, start, providerRef | Avoid duplicate reminders |
| EV-03 | AttendanceRecorded | Attendance | Reporting, absence alerts | sessionId, learnerId, status | Idempotent alert evaluation |
| EV-04 | QuestionReviewed | Assessment | Assessment publication | questionId, reviewerDecision | Reject unapproved publication |
| EV-05 | AssessmentSubmitted | Assessment | Grade/academic record | attemptId, submittedAt | One final submission |
| EV-06 | GradeFinalized | Assessment | Academic records, reports | gradeId, version | No duplicate grade mutation |
| EV-07 | CertificateIssued | Credentials | DigiLocker, notification | certificateId, number | No duplicate issue |
| EV-08 | NotificationRequested | Notifications | Delivery adapters | notificationId, templateId | Retry + dedup + provider callback |
| EV-09 | MediaAssetReady | Media | Content/search projection | assetId, contentVersion | DRM/permission check |
| EV-10 | AuditEvidenceAnchored | Platform | Compliance storage | auditBatchId, integrityRef | Tamper evidence verification |

# 18. Six source-defined roles — unchanged

| Role | Source-described responsibility | Proposed least-privilege boundary | Authorization scope | Open approval |
| --- | --- | --- | --- | --- |
| University Super Admin | University-wide administration | Administration only within formally approved University tenant; sensitive changes require strong auth and audit | University / all institutions? | Exact privileges and cross-institution scope OPEN |
| SPC Admin | SPC administration | Scoped to explicitly assigned SPC jurisdiction and linked institutions | SPC / jurisdiction | SPC-to-institution cardinality OPEN |
| Institution Admin | Institution administration | Scoped to assigned institution, not automatically all SPC or University data | Institution | Whether one person may administer multiple institutions OPEN |
| Faculty/Educator | Teaching and course activities | Only courses/classes and learner records explicitly assigned | Course / institution | Course sharing and co-author review rights OPEN |
| Student/Learner | Learning and personal academic activities | Own enrollments, assessments, attendance, results and approved learning resources | Self / enrollment | Guardian, transfer, lifetime account mapping OPEN |
| Registered Pharmacist | Professional learning role | Only authorized pharmacist learning/credential features after identity verification | Self / verified professional identity | Exact differentiation from Student and professional verification OPEN |

# 19. Full 55-object logical catalogue — Part A

| Object ID | Candidate object | Attributes from Day 4 | Day 2 RTM |
| --- | --- | --- | --- |
| ORG-01 | University | university_id, display_name, status | IAM-001, IAM-016 |
| ORG-02 | SPC jurisdiction | spc_id, name, parent_reference | IAM-002, IAM-016 |
| ORG-03 | Institution | institution_id, name, organization_reference | IAM-003, IAM-016 |
| IAM-OBJ-01 | User identity | user_id, identity_provider_ref, status | IAM-007..015 |
| IAM-OBJ-02 | Role definition | role_id, role_code, role_name | IAM-001..008 |
| IAM-OBJ-03 | Permission | permission_id, resource, action | IAM-008, IAM-017 |
| IAM-OBJ-04 | Role–permission grant | role_id, permission_id, scope | IAM-008, IAM-017 |
| IAM-OBJ-05 | User membership/role assignment | user_id, organization_id, role_id, validity | IAM-007..008, IAM-016 |
| IAM-OBJ-06 | Provisioning/import batch | batch_id, initiator, outcome | IAM-018..020 |
| IAM-OBJ-07 | External SSO link | user_id, provider, subject_ref | IAM-015 |

# 19. Full 55-object logical catalogue — Part B

| Object ID | Candidate object | Attributes from Day 4 | Day 2 RTM |
| --- | --- | --- | --- |
| ACD-OBJ-01 | Programme | programme_id, name, status | ACD-001 |
| ACD-OBJ-02 | Year/Semester | period_id, programme_id, label | ACD-002 |
| ACD-OBJ-03 | Subject | subject_id, period_id, title | ACD-003 |
| ACD-OBJ-04 | Topic | topic_id, subject_id, title | ACD-004 |
| ACD-OBJ-05 | Course | course_id, academic_ref, status | ACD-005 |
| ACD-OBJ-06 | Course prerequisite | course_id, required_course_ref, rule | ACD-006 |
| ACD-OBJ-07 | Content item | content_id, course_ref, content_type | ACD-005, ACD-020 |
| ACD-OBJ-08 | Content version | content_id, version, approval_state | ACD-008..009 |
| ACD-OBJ-09 | Content contributor | content_id, user_id, contribution_role | ACD-007 |
| ACD-OBJ-10 | Content approval event | version_ref, actor, transition, timestamp | ACD-008..009 |
| ACD-OBJ-11 | Live class session | session_id, course_ref, provider_ref | ACD-010..015 |
| ACD-OBJ-12 | Class schedule | session_id, planned_time, resource_ref | ACD-018..019 |
| ACD-OBJ-13 | Recording / transcript metadata | session_id, asset_ref, transcript_ref | ACD-015..017 |
| ACD-OBJ-14 | Library index record | content_ref, title, searchable_text_ref | ACD-020..023 |

# 19. Full 55-object logical catalogue — Part C

| Object ID | Candidate object | Attributes from Day 4 | Day 2 RTM |
| --- | --- | --- | --- |
| ASM-OBJ-01 | Attendance record | session_ref, person_ref, status, time | ASM-001..004 |
| ASM-OBJ-02 | Absence notification trigger | attendance_ref, recipient_scope, status | ASM-002..004 |
| ASM-OBJ-03 | Question bank item | question_id, subject_ref, version, state | ASM-005 |
| ASM-OBJ-04 | AI question draft | draft_id, prompt_ref, reviewer_status | ASM-006..007 |
| ASM-OBJ-05 | SME review decision | draft_ref, reviewer_ref, decision, timestamp | ASM-007 |
| ASM-OBJ-06 | Assessment definition | assessment_id, chapter_ref, delivery_scope | ASM-008..009 |
| ASM-OBJ-07 | Assessment attempt / response | attempt_id, learner_ref, response_ref | ASM-008..011 |
| ASM-OBJ-08 | Grade / grading event | attempt_ref, grader_ref, score, event | ASM-010..011 |
| ASM-OBJ-09 | Assignment | assignment_id, course_ref, due_rule | ASM-012..013 |
| ASM-OBJ-10 | Assignment submission | assignment_ref, learner_ref, submission_ref | ASM-012..013 |
| ASM-OBJ-11 | Practical logbook entry | learner_ref, practical_ref, evidence_ref | ASM-014 |
| ASM-OBJ-12 | Marksheets | marksheet_id, learner_ref, signature_ref | ASM-015..016 |
| ASM-OBJ-13 | Lifetime academic record | learner_ref, record_ref, achievement_ref | ASM-017 |
| ASM-OBJ-14 | Certificate | certificate_id, unique_number, learner_ref | ASM-018..023 |
| ASM-OBJ-15 | Certificate verification | certificate_ref, verification_token, state | ASM-021..022 |
| ASM-OBJ-16 | Credential integration receipt | certificate_ref, provider_ref, result | ASM-023 |

# 19. Full 55-object logical catalogue — Part D

| Object ID | Candidate object | Attributes from Day 4 | Day 2 RTM |
| --- | --- | --- | --- |
| COM-OBJ-01 | Dashboard/report definition | report_id, owner_scope, specification | COM-001..009 |
| COM-OBJ-02 | Reporting projection | source_ref, metric_key, period, value | COM-006..009, COM-022 |
| COM-OBJ-03 | Forum / discussion item | thread_id, course_ref, author_ref | COM-010 |
| COM-OBJ-04 | Announcement | announcement_id, audience_scope, message | COM-011 |
| COM-OBJ-05 | Platform message | message_id, sender_ref, recipient_scope | COM-012 |
| COM-OBJ-06 | Academic calendar event | event_id, academic_scope, start_time | COM-013 |
| COM-OBJ-07 | Notification template | template_id, channel, version | COM-014..020 |
| COM-OBJ-08 | Notification request | request_id, event_ref, channel, status | COM-014..019 |
| COM-OBJ-09 | Delivery attempt/receipt | request_id, provider_ref, delivery_state | COM-021 |
| MOB-OBJ-01 | Playback/bookmark/notes | learner_ref, media_ref, position, note_ref | MOB-015..021 |
| MOB-OBJ-02 | Device notification preference | user_ref, channel, preference | MOB-023..025 |
| MOB-OBJ-03 | Offline cache manifest | device_ref, asset_ref, expiry | MOB-026 |
| SEC-OBJ-01 | Tamper-evident audit event | event_id, actor, action, integrity_ref | IAM-020, SEC-005..007, SEC-016 |
| OPS-OBJ-01 | Test / acceptance evidence | test_id, RTM_id, result, evidence_ref | OPS-005..010 |
| OPS-OBJ-02 | External integration transaction | integration_id, provider, correlation_ref, status | IAM-015, ASM-023, COM-018 |

# 20. Day 3 clarifications — all 22 unchanged

| Clarification ID | Decision required (unchanged) | Proposed owner | Status |
| --- | --- | --- | --- |
| D3-CL-01 | University / SPC / Institution parent-child cardinalities and whether hierarchy can change | University sponsor | OPEN |
| D3-CL-02 | Whether one person may hold multiple roles and roles in multiple institutions | University IAM owner | OPEN |
| D3-CL-03 | Approved permission matrix per role and tenant, including pharmacist access | University IAM owner | OPEN |
| D3-CL-04 | Student enrolment ownership and transfer between institutions | Academic SME | OPEN |
| D3-CL-05 | Academic taxonomy reuse and relationship between Course and Programme/Subject/Topic | Academic SME | OPEN |
| D3-CL-06 | Prerequisite equivalence, overrides and cycle prevention | Academic SME | OPEN |
| D3-CL-07 | Content approver authority, publish/rollback, version immutability | Content SME | OPEN |
| D3-CL-08 | Live class attendance source, scheduling conflict rules, recording retention | Academic/IT SME | OPEN |
| D3-CL-09 | Question/SME reviewer authorization, AI data-sharing and audit expectations | Assessment SME | OPEN |
| D3-CL-10 | Assessment attempt, retake, grading, correction and result-release rules | Assessment SME | OPEN |
| D3-CL-11 | Lifetime record meaning, correction, archival and migration | Registrar | OPEN |
| D3-CL-12 | Certificate revocation/reissue, QR public data fields, signing authority | Registrar | OPEN |
| D3-CL-13 | Report metric definitions, MPR format, SLA calculations and data freshness | University reporting owner | OPEN |
| D3-CL-14 | Notification preference precedence, provider retries, retention and consent | University communications owner | OPEN |
| D3-CL-15 | Mobile offline scope, cache expiry, synchronization and conflict resolution | Mobile/product owner | OPEN |
| D3-CL-16 | Concurrency workload definition, API latency targets, content volumes | University technical owner | OPEN |
| D3-CL-17 | Provider contracts/sandbox credentials for SSO, live class, DigiLocker, messaging, DRM | Integration owners | OPEN |
| D3-CL-18 | Data classification, retention schedule (except explicit obligations), deletion and legal holds | University security/legal | OPEN |
| D3-CL-19 | Payment scope: title/service label exists, but no defined payment business workflow | University business owner | OPEN |
| D3-CL-20 | Formal approval of 120-working-day plan against source 12-week roadmap | University sponsor / PMO | OPEN |
| D3-CL-21 | Who approves ERD, schema changes and organization-scoped data access | University sponsor / architecture board | OPEN |
| D3-CL-22 | Role-specific data access and reporting for Registered Pharmacist | University business owner | OPEN |

# 21. Day 5 decisions — all 12 unchanged

| Decision ID | Question / decision (unchanged) | Status |
| --- | --- | --- |
| D5-DEC-01 | Select PostgreSQL deployment/version, extension policy and India regions | OPEN — approval required |
| D5-DEC-02 | Approve UUID/BIGINT primary key strategy per domain | OPEN — approval required |
| D5-DEC-03 | Approve tenant-scoping and RLS strategy after organizational cardinalities | OPEN — approval required |
| D5-DEC-04 | Approve schema/service ownership and cross-domain data exchange | OPEN — approval required |
| D5-DEC-05 | Approve academic/attendance/assessment uniqueness grains | OPEN — approval required |
| D5-DEC-06 | Approve record retention, legal holds and correction workflows | OPEN — approval required |
| D5-DEC-07 | Approve index/workload measurement and partition thresholds | OPEN — approval required |
| D5-DEC-08 | Approve schema migration tooling, release controls and DBA access | OPEN — approval required |
| D5-DEC-09 | Approve backup, PITR and geo-DR topology with measured drills | OPEN — approval required |
| D5-DEC-10 | Approve public certificate verification data disclosure policy | OPEN — approval required |
| D5-DEC-11 | Approve outbox/integration replay semantics | OPEN — approval required |
| D5-DEC-12 | Approve Day 5 physical baseline before implementation | OPEN — approval required |

# 22. Day 6 decisions — all 14 unchanged

| Decision ID | Open decision | Status |
| --- | --- | --- |
| D6-DEC-01 | Approve bounded context ownership and deployable service grouping | OPEN — no approval recorded |
| D6-DEC-02 | Approve OpenAPI versioning, compatibility and deprecation rules | OPEN — no approval recorded |
| D6-DEC-03 | Approve identity token flow, SSO callback and six-role resource authorization matrix | OPEN — no approval recorded |
| D6-DEC-04 | Approve OTP/MFA/session semantics and anti-abuse controls | OPEN — no approval recorded |
| D6-DEC-05 | Approve state transitions and approval owners for course publishing | OPEN — no approval recorded |
| D6-DEC-06 | Approve live-class provider contracts, calendar conflict and webhook rules | OPEN — no approval recorded |
| D6-DEC-07 | Approve question SME-review and assessment/attendance business idempotency | OPEN — no approval recorded |
| D6-DEC-08 | Approve certificate signing, DigiLocker handoff, correction and disclosure rules | OPEN — no approval recorded |
| D6-DEC-09 | Approve notification channel adapters, retry windows and templates | OPEN — no approval recorded |
| D6-DEC-10 | Approve event delivery semantics, outbox ownership and retention | OPEN — no approval recorded |
| D6-DEC-11 | Approve mobile offline synchronization and DRM authorization | OPEN — no approval recorded |
| D6-DEC-12 | Approve 500k-user workload, rate limits, SLOs and contract-test gates | OPEN — no approval recorded |
| D6-DEC-13 | Approve data residency and VAPT scope across external providers | OPEN — no approval recorded |
| D6-DEC-14 | Approve API security/privacy review and contract sign-off process | OPEN — no approval recorded |

# 23. Day 7 decisions — all 12 unchanged

| Decision ID | Decision / required owner | Status |
| --- | --- | --- |
| D7-DEC-01 | Approve six-role permission matrix by action and resource scope | OPEN — not approved |
| D7-DEC-02 | Resolve University/SPC/institution hierarchy and cross-tenant exception policy | OPEN — not approved |
| D7-DEC-03 | Confirm multi-role membership, delegation, session scope and role revocation | OPEN — not approved |
| D7-DEC-04 | Approve Registrar signing authority without inventing seventh role | OPEN — not approved |
| D7-DEC-05 | Approve SSO token mapping, OTP/MFA flows and session lifecycle | OPEN — not approved |
| D7-DEC-06 | Approve service-to-service trust, broker ACL and callback verification | OPEN — not approved |
| D7-DEC-07 | Approve provider inventory, contracts, sandboxes and India residency evidence | OPEN — not approved |
| D7-DEC-08 | Approve media DRM, recording entitlement and offline revocation rules | OPEN — not approved |
| D7-DEC-09 | Approve public QR verifier minimal response and anti-abuse rules | OPEN — not approved |
| D7-DEC-10 | Approve notification channel consent, templates and retry policy | OPEN — not approved |
| D7-DEC-11 | Approve security acceptance test evidence, VAPT and remediation gate | OPEN — not approved |
| D7-DEC-12 | Approve Day 7 authorization and integration contract baseline | OPEN — not approved |

# 24. Day 8 decisions — all 14 unchanged

| ID | Decision | State |
| --- | --- | --- |
| D8-DEC-01 | Approve integration owners, provider inventory and sandbox access | OPEN — approval required |
| D8-DEC-02 | Approve exact SSO/Digi-Pharmed/PRTS identity mapping and trust contracts | OPEN — approval required |
| D8-DEC-03 | Approve DigiLocker onboarding, Registrar signing and certificate disclosures | OPEN — approval required |
| D8-DEC-04 | Approve live-class/recording provider and concurrency entitlements | OPEN — approval required |
| D8-DEC-05 | Approve DRM/CDN/media residency and offline revocation behavior | OPEN — approval required |
| D8-DEC-06 | Approve messaging providers, consent, templates and rate quotas | OPEN — approval required |
| D8-DEC-07 | Approve AI question-generation data handling and SME review contract | OPEN — approval required |
| D8-DEC-08 | Approve end-to-end sequence and failure handling contracts | OPEN — approval required |
| D8-DEC-09 | Approve 500k concurrency interpretation and workload profile | OPEN — approval required |
| D8-DEC-10 | Approve p95/p99, TPS, soak duration and error thresholds (not in source) | OPEN — approval required |
| D8-DEC-11 | Approve India residency, audit retention and DR evidence methods | OPEN — approval required |
| D8-DEC-12 | Approve integration harness and synthetic data policies | OPEN — approval required |
| D8-DEC-13 | Approve CERT-In VAPT engagement, remediation and mobile security gate | OPEN — approval required |
| D8-DEC-14 | Approve Day 8 baseline and Day 9 transition | OPEN — approval required |

# 25. Day 9 decisions — all 12 unchanged

| Decision ID | Required approval | Status |
| --- | --- | --- |
| D9-DEC-01 | Approve 120-day stage allocations, gates and acceptance owners | OPEN — not approved |
| D9-DEC-02 | Approve baseline calendar, working-day definition, holidays and start date | OPEN — not approved |
| D9-DEC-03 | Approve detailed WBS, RTM mapping and scope exclusions | OPEN — not approved |
| D9-DEC-04 | Approve team availability, role mix, ramp-up and budget | OPEN — not approved |
| D9-DEC-05 | Approve three-point effort estimates, risk reserves and contingency | OPEN — not approved |
| D9-DEC-06 | Approve provider procurement, onboarding lead times and contractual SLAs | OPEN — not approved |
| D9-DEC-07 | Approve true CPM network after precedence and durations are supplied | OPEN — not approved |
| D9-DEC-08 | Approve 500k workload model and measurable NFR acceptance thresholds | OPEN — not approved |
| D9-DEC-09 | Approve VAPT, DR, UAT and mobile-store lead-time reservations | OPEN — not approved |
| D9-DEC-10 | Approve risk appetite, escalation thresholds and decision SLAs | OPEN — not approved |
| D9-DEC-11 | Approve Day 10 scope/design readiness pack inputs | OPEN — not approved |
| D9-DEC-12 | Authorize or withhold transition beyond discovery gate | OPEN — not approved |

# 26. Day 10 decisions — unchanged

| ID | Decision required | State |
| --- | --- | --- |
| D10-DEC-01 | Accept Day 2 original RTM as controlled reference after atomic wording audit | OPEN — not approved |
| D10-DEC-02 | Approve or reject critical tenancy and role assumptions | OPEN — not approved |
| D10-DEC-03 | Approve clarification ownership and resolution dates | OPEN — not approved |
| D10-DEC-04 | Approve provider dependency plan and fallback decisions | OPEN — not approved |
| D10-DEC-05 | Approve source-defined and proposed NFR acceptance measures separately | OPEN — not approved |
| D10-DEC-06 | Approve architecture traceability and security gate criteria | OPEN — not approved |
| D10-DEC-07 | Approve staffing/estimation assumptions and risk contingencies | OPEN — not approved |
| D10-DEC-08 | Decide G-D10: GO, CONDITIONAL GO or NO-GO with evidence | OPEN — not approved |
| D10-DEC-09 | Approve next-phase authority and exclusions | OPEN — not approved |
| D10-DEC-10 | Approve baseline versioning and PR review controls | OPEN — not approved |

# 27. Day 14 exit gate and Day 15 handoff

No implementation authorization: Day 10 NO-GO recommendation remains active until a recorded University gate decision supersedes it.

Before approval, obtain reviewed configuration matrices, CI/CD gates, rollback and migration plans, named owners, environment evidence and approved NFR acceptance measures.

For Day 15, propose architecture security review, data-flow threat modelling, technical design closure and evidence-driven ADR review; do not assume unresolved provider or University decisions have been answered.

Every change must retain original requirement IDs and cite source/approval evidence; the Word file is a draft design artifact, not proof of a deployed pipeline.

# 28. Approval register

| Review role | Disposition | Date / evidence |
| --- | --- | --- |
| University Product Owner | PENDING | — |
| Solution Architect | PENDING | — |
| Security / Privacy Owner | PENDING | — |
| DevOps / Platform Lead | PENDING | — |
| DBA | PENDING | — |
| QA / Performance Lead | PENDING | — |
| SRE / Operations | PENDING | — |
| Delivery Manager | PENDING | — |